## Executive Summary
| April 2024 Monthly Project Progress Report |  | Questions or feedback? Contact the CSP Program Administrator at info@oregoncsp.org
Executive Summary |  | Status of all CSP Projects
|  | Utility | # of Pre-Certified Projects | # of Certified Projects | # of Operational Projects | Total Projects in Program
|  | IP | 1 | 0 | 0 | 1
|  | PAC | 24 | 3 | 6 | 33
|  | PGE | 17 | 1 | 13 | 31
|  | Total | 42 | 4 | 19 | 65
Status of Pre-certified and Certified Projects Only (excludes operational projects)
|  | Utility | # of Projects | Avg # of Months Since Pre-Certification | # of Projects with Ownership Tranfers | # of Projects Granted Certification Extensions | # of Projects Citing Development Delays* | # of Projects Citing Interconnection Delays*
|  | IP | 1 | 45.5592 | 0 | 1 | 1 | 0
|  | PAC | 27 | 29.1849 | 17 | 26 | 21 | 18
|  | PGE | 17 | 23.6803 | 13 | 13 | 11 | 7
|  | Total | 46 | N/A | 30 | 40 | 33 | 25
*based on information provided by Project Managers in requests for Certification extensions
Viewing Project Data in this Report
This report includes two additional project data tables accessible via the tabs below that include specific project data and that allow users to sort on a range of specific parameters.
CSP Project Data This sheet provides a range of specific data for all Pre-Certified, Certified and Operational projects in the Program. Each column in the table allows for users to sort the projects on specific parameters.
OPUC Project Decisions This sheet includes the history of OPUC decisions for CSP projects, beginning with Pre-Certification and through Certification. Users can sort on a range of parameters and access PA recommendations and Commission decisions that have been posted to Docket No. UM 1930.
Beginning in April 2024, the Community Solar Program Administrator (PA) will produce monthly-updated CSP project reports. The PA and OPUC Staff intend for the reports to provide all parties with timely and updated information for tracking project progress, with a focus on identifying and mitigating avoidable delays, increasing transparency and accountability, and improving Program performance. The reports are an important next step in the PA and OPUC Staff's broader plan to reduce additional project development and interconnection delays.
In developing this first monthly report, the PA finds the following:
Most (71%) of the Program's Pre-Certified and Certified (i.e., non-operational) projects have experienced non-interconnection development delays, with 77% of projects in PacifiCorp service area and 65% in PGE service area. The single project in Idaho Power service area has also experienced development delays.
Across all projects, development delays have been primarily related to national supply chain issues and construction delays. A few projects have experienced delays due to project financing as well as customer enrollment.
Almost half (41%) of non-operational projects in PGE's service area have reported experiencing interconnection delays.
Two-thirds (67%) of non-operational projects in PacifiCorp's service area have reported experiencing interconnection delays.
It is a common practice for project developers to transfer ownership of a project to another parent entity after Pre-Certification and prior to Certification. Almost two-thirds (65%) of all Pre-Certified and Certified projects have been transfered.
In developing this report, the PA has found opportunities to improve the consistency of data collection from projects. With those improvements and OPUC Staff's enhanced collection of data from the utilities, the PA expects to make ongoing improvements to this report in the coming months. Finally, the PA welcomes and encourages input from stakeholders on how to make the report increasingly valuable and effective in support of improving overall Program performance.

## CSP Project Data
2024-04-19
CSP Project Data
Utility Queue Number | Utility Service Area | CSP Project ID | Project Name | CSP Project Status | Initial owner entity/parent owner entity | Current owner entity/parent owner entity | Pre-Certification Date | Prior Certification Deadlines | Current Certification Deadline / Date Certified | Months Since Pre-Certification (Pre-certified & Certified Projects Only) | Months from Pre-Certification to Certification (Operational Projects Only) | Prior Commercial Operating Date(s) (COD) - Utility Provided | Current COD - Utility Provided | Months from Pre-Certification to Current COD - Utility Provided | Have Public Utility and Applicant Agreed to Revised Schedule? Utility Provided | History of Parent Entity Ownership transfers? | History of Project Development Delays? (Based Only on Project Reporting) | History of Interconnection Delays? (Based Only on Project Reporting) | Most Recent Project Recommendation Posted to Docket No. UM 1930
OCS038 | PAC | PP-2021-112 | 7 Mile Solar | Pre-Certified | TLS Capital | Luminace | 2022-04-15 | 10/15/2023, 12/14/2023 | 2024-06-11 | 24.1776 | Not Yet Certified | 8/15/2022, 12/9/2022, 7/21/2023 | 2024-09-27 | 29.4737 | Yes | Yes | No | Yes; IX work incomplete- fiber optic material not ordered; IX design incomplete | 2/22/2024 - Cert Extension Request
OCS046 | PAC | PP-2021-109 | Antelope Creek Solar | Pre-Certified | TLS Capital | Luminace | 2022-04-15 | 10/15/2023, 1/15/2024 | 2024-04-15 | 24.1776 | Not Yet Certified | 8/15/2022, 12/16/2022, 7/28/2023 | 2024-06-21 | 26.25 | Yes | Yes | Yes; low-income enrollment incomplete | Yes; IX work incomplete | 3/8/2024- Cert Extension Request
SPQ0266 | PGE | PGE-2023-157 | Apricus Solar LLC | Pre-Certified | Conifer Energy Partners | Conifer Energy Partners | 2023-07-17 | NA | 2025-01-17 | 9.1118 | Not Yet Certified | Data Not Available | Data Not Available | Data Not Available | Data Not Available | Yes | No | No | Pre-certification
SPQ0250 | PGE | PGE-2020-75 | Auburn Solar | Pre-Certified | Sulus | SolRiver LLC | 2022-04-15 | 2023-10-15 | 2024-04-15 | 24.1776 | Not Yet Certified | Data Not Available | Data Not Available | Data Not Available | Data Not Available | Yes | Yes; equipment procurement | Yes; unspecified | 11/11/2023 - Cert Extension Request
SPQ0186 | PGE | PGE-2020-15 | Belvedere Solar | Pre-Certified | SPI | Luminace | 2020-08-07 | 2/7/2022, 8/7/2022, 2/7/2023, 8/7/2023 | 2024-08-19 | 44.4408 | Not Yet Certified | 2021-06-21 | 2024-07-26 | 47.6645 | Yes | Yes | Yes; COVID-19, US Dept of Commerce investigation; | Yes; IX construction delays | 8/26/2023 - Cert Extension Request
OCS055 | PAC | PP-2021-125 | Blackwell Creek Solar | Pre-Certified | TLS Capital | TLS Capital | 2023-05-12 | NA | 2024-11-12 | 11.2829 | Not Yet Certified | Not Applicable | 2023-10-27 | 5.5263 | In Negotiation | No | No | No | Pre-certification
OCS062 | PAC | PP-2021-104 | Buckaroo Solar 1 LLC | Pre-Certified | Sunthurst | Sunthurst | 2022-05-02 | 2023-11-23 | 2024-11-23 | 23.6184 | Not Yet Certified | 2023-07-21 | 2025-09-30 | 41.0197 | Yes | No | Yes; COVID-19, US Dept of Commerce investigation; construction delays; | Yes; revised interconnection schedule | 4/5/2024- Cert Extension Request
OCS063 | PAC | PP-2021-103 | Buckaroo Solar 2 | Pre-Certified | Sunthurst | Sunthurst | 2022-05-02 | 2023-11-23 | 2024-11-23 | 23.6184 | Not Yet Certified | 2023-07-21 | 2025-09-30 | 41.0197 | Yes | No | Yes; COVID-19, US Dept of Commerce investigation; construction delays; | Yes; revised interconnection schedule | 4/5/2024- Cert Extension Request
SPQ0191 | PGE | PGE-2020-21 | Buckner Creek Solar LLC | Pre-Certified | Conifer Energy Partners | Conifer Energy Partners | 2022-04-15 | 2023-08-15 | 2024-12-31 | 24.1776 | Not Yet Certified | 2020-11-30 | 2024-12-04 | 31.7105 | Yes | No | Yes; contractor schedule constraints; inability to construct during winter | No | 10/13/2023 - Cert Extension Request
OCS041 | PAC | PP-2021-95 | Burg Solar | Pre-Certified | Sulus | SolRiver LLC | 2022-04-15 | 2023-10-15 | 2024-09-30 | 24.1776 | Not Yet Certified | 9/23/2022 | 2024-12-06 | 31.7763 | Yes | Yes | No | No | 6/3/2023 - PM Transfer
OCS008 | PAC | PP-2020-76 | Burlingame Solar LLC | Pre-Certified | Sulus | SolRiver LLC | 2020-12-29 | 12/29/2023, 6/29/2022, 6/30/2023 | 2024-09-30 | 39.7039 | Not Yet Certified | 5/17/2022, 3/17/2022 | 2024-09-06 | 44.3092 | Yes | Yes | Yes; US Dept of Commerce investigation; uncertainty of Tier 2 capacity release | No | 7/27/2022 - Cert Extension Request
OCS050 | PAC | PP-2021-94 | Canyonville Solar 1 | Pre-Certified | Sulus | SolRiver LLC | 2022-05-11 | 2023-11-11 | 2024-09-11 | 23.3224 | Not Yet Certified | 11/4/2022 | 2023-06-23 | 13.4211 | Data Not Available | Yes | Yes; supply chain delays | Yes; waiting for revised IX timeline from PAC | 6/10/2023 -Cert Extension Request
OCS051 | PAC | PP-2022-142 | Canyonville Solar 2 | Pre-Certified | Sulus | SolRiver Capital | 2022-05-12 | 2023-11-12 | 2024-09-12 | 23.2895 | Not Yet Certified | 11/4/2022 | 2023-06-23 | 13.3882 | Data Not Available | Yes | Yes; supply chain delays | Yes; waiting for revised IX timeline from PAC | 6/10/2023 -Cert Extension Request
OCS049 | PAC | PP-2021-113 | Chapman Creek Solar | Pre-Certified | TLS Capital | Luminace | 2022-04-15 | 2023-10-15 | 2024-10-15 | 24.1776 | Not Yet Certified | 11/30/2022, 10/31/2023 | 2024-10-18 | 30.1645 | Yes | Yes | Yes; contractor schedule constraints; inability to construct during witner | Yes; unspecified | 11/12/2023 - Cert Extension Request
SPQ0158 | PGE | PGE-2020-56 | Carnes Creek Solar LLC | Operational | Conifer Energy Partners | Conifer Energy Partners | 2020-06-12 | 12/12/2021, 6/12/2022 | 2022-12-14 | 46.2829 | 30.0987 | Data Not Available | Data Not Available | Data Not Available | Data Not Available | No | Yes; COVID-19, US Dept of Commerce investigation | No | NA
OCS058 | PAC | PP-2021-121 | Coker Solar | Pre-Certified | Sulus | Hawthorne Renewables | 2023-05-12 | NA | 2024-11-12 | 11.2829 | Not Yet Certified | 3/24/2023, 3/22/2024 | 2025-05-30 | 24.6382 | Yes | Yes | No | No | 9/27/2023 - Cert Extension Request
SPQ0180 | PGE | PGE-2020-17 | Clayfield Solar LLC | Pre-Certified | Solar Town | Luminace | 2020-07-17 | 1/17/2023, 7/17/2023 | 2024-06-30 | 45.1316 | Not Yet Certified | 2021-03-26 | 2024-07-24 | 48.2895 | Yes | Yes | Yes; COVID-19, US Dept of Commerce investigation, timeline changes due to federal ITC | Yes; IX construction delays | 8/26/2023 - Cert Extension Request
SPQ0193 | PGE | PGE-2020-19 | Dover Solar | Pre-Certified |  | Luminace | 2020-07-01 | 2/1/2022, 8/1/2022, 7/1/2023, 2/29/2024 | 2024-08-27 | 45.6579 | Not Yet Certified | 2020-11-06 | 2024-08-07 | 49.2763 | Yes | Yes | Yes; COVID-19, US Dept of Commerce investigation; construction delays; customer enrollment | Yes; unspecified | 4/5/2024 - Cert Extension Request
OCS012 | PAC | PP-2020-63 | Goodling Annex | Pre-Certified | Bonneville Environmental Foundation | Bonneville Environmental Foundation | 2020-04-21 | 10/21/2021, 4/1/2023 | 2024-02-28 | 47.9934 | Not Yet Certified | 2022-05-30 | 2023-05-30 | 37.3026 | In Negotiation | No | Yes; waiting for grant funding | No | 4/5/2024 - Cert Extension Request
OCS045 | PAC | PP-2021-99 | Green Solar | Pre-Certified | Greenkey Solar | SolRiver Capital | 2022-04-15 | 2023-10-15 | 2024-06-15 | 24.1776 | Not Yet Certified | Not Applicable | 2022-10-21 | 6.2171 | No | Yes | No | Yes; IX construction delays | 11/12/2023 - Cert Extension Request
SPQ0220 | PGE | PGE-2020-11 | Cork Solar LLC | Pre-Certified | Solar Town | SPI Solar Inc | 2022-05-02 | 2023-11-02 | 2024-08-31 | 23.6184 | Not Yet Certified | Data Not Available | Data Not Available | Data Not Available | Data Not Available | Yes | Yes; construction delays | Yes; IX construction delays | 8/26/2023 - Cert Extension Request
OCS039 | PAC | PP-2021-97 | Kelly Creek Solar | Pre-Certified | Coast Energy, LLC | Coast Energy, LLC | 2022-04-15 | 2023-10-15 | 2024-10-30 | 24.1776 | Not Yet Certified | 11/18/2022 | 2023-09-30 | 17.5329 | In Negotiation | No | Yes; contractor schedule constraints; inability to construct during witner | No | 11/12/2023 - Cert Extension Request
SPQ0152 | PGE | PGE-2020-34 | Cosper Creek Solar LLC | Operational | TLS Capital | HEP | 2020-06-12 | 12/12/2021, 6/12/2022, 12/12/2022 | 2022-12-14 | 46.2829 | 30.0987 | Not Applicable | 2022-01-14 | 19.1118 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation | No | NA
OCS025 | PAC | PP-2020-80 | Linkville Solar | Certification | TLS Capital | Luminace | 2020-11-17 | 5/17/2022, 11/17/2022, 5/17/2023, 11/17/2023 | 2024-03-30 | 41.0855 | Not Yet Certified | 10/29/2021 | 2023-08-31 | 33.4539 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation; | Yes; fiber work delayed | 6/10/2023- Cert Extension Request
OCS027 | PAC | PP-2020-82 | Marble Solar | Pre-Certified | Sulus | SolRiver Capital | 2020-12-29 | 12/29/2021, 6/29/2022, 9/30/2023 | 2024-07-30 | 39.7039 | Not Yet Certified | 10/29/2021 | 2022-04-29 | 15.9868 | In Negotiation | Yes | Yes; US Dept of Commerce investigation; uncertainty of Tier 2 capacity release; wetland permitting delays | Yes; awaiting updated IX agreement | 6/10/2023- Cert Extension Request
SPQ0157 | PGE | PGE-2020-37 | Gun Club Solar LLC | Pre-Certified |  | Luminace | 2022-04-15 | 2023-10-15 | 2024-10-31 | 24.1776 | Not Yet Certified | 2019-12-01 | 2024-10-31 | 30.5921 | Yes | Yes | Yes; contractor schedule constraints; inability to construct during witner | No | 8/26/2023 - Cert Extension Request
SPQ0094 | PGE | PGE-2020-42 | Kaiser Creek Solar LLC | Operational | HEP | GreenKey Solar | 2020-06-18 | 12/18/2021, 6/12/2022, 12/18/2022 | 2022-12-14 | 46.0855 | 29.9013 | Data Not Available | Data Not Available | Data Not Available | Data Not Available | Yes | Yes; COVID-19, US Dept of Commerce investigation | No | NA
CSQ0004 | PGE | PGE-2021-115 | Mompano Solar | Pre-Certified | Greenkey Solar | Coast Energy, LLC | 2022-04-15 | 2023-10-15 | 2024-10-30 | 24.1776 | Not Yet Certified | Data Not Available | Data Not Available | Data Not Available | Data Not Available | Yes | Yes; contractor schedule constraints; inability to construct during winter | No | 11/11/2023 - Cert Extension Request
OCS035 | PAC | PP-2021-111 | Orchard Knob Solar | Pre-Certified | TLS Capital | Luminace | 2022-04-15 | 10/15/2023, 1/15/2024 | 2024-09-11 | 24.1776 | Not Yet Certified | 8/19/2022, 11/21/2022, 3/24/2023, 2/23/2024 | 2024-09-13 | 29.0132 | Yes | Yes | Yes; time to provide relevant certification documents | Yes; IX work incomplete - material not ordered, waiting for revised IX timeline, confirm outstanding easements | 3/8/2024 - Cert Extension Request
OCS057 | PAC | PP-2020-88 | Perrydale Solar | Pre-Certified | Sulus; Sol River Capital | Evergreen | 2022-04-15 | 10/15/2023, 12/31/2023 | 2024-08-05 | 24.1776 | Not Yet Certified | 3/3/2023, 7/21/2023 | 2024-08-09 | 27.8618 | Yes | Yes | No | Yes; equipment lead times and crew availability | 1/5/2024 - Cert Extension Request
Q0666 | PAC | PP-2020-13 | Pilot Rock Solar 1 | Pre-Certified | Sunthurst | Sunthurst | 2020-03-11 | 10/11/2021, 3/15/2024 | 2025-09-30 | 49.3421 | Not Yet Certified | 2015-12-31 | 2025-09-30 | 66.7434 | Data Not Available | No | Yes; COVID-19, lingering impacts of the US commerce investigation | Yes; delays in securing a utility PPA and IX agreement | 8/17/2023 - Cert Extension Request
Q1045 | PAC | PP-2020-71 | Pilot Rock Solar 2 | Pre-Certified | Sunthurst | Sunthurst | 2020-04-21 | 10/21/2021, 3/15/2023 | 2025-09-30 | 47.9934 | Not Yet Certified | 2019-12-31 | 2025-09-30 | 65.3947 | Data Not Available | No | Yes; COVID-19, lingering impacts of the US commerce investigation | Yes; delays in securing a utility PPA and interconnection agreement | 8/17/2023 - Cert Extension Request
OCS036 | PAC | PP-2020-84 | Pine Grove Solar | Certification | TLS Capital | Luminace | 2020-12-29 | 6/29/2022, 12/29/2022, 8/25/2023 | 2023-10-18 | 39.7039 | Not Yet Certified | 8/5/2022, 11/15/2022, 8/21/2023 | 2024-02-16 | 37.6316 | Yes | Yes | Yes; COVID-19, US Dept of Commerce investigation; | Yes; delayed utility timeline | 10/18/2023 - Certification
SPQ0272 | PGE | PGE-2023-167 | Lincoln Solar LLC | Pre-Certified | Conifer Energy Partners | Conifer Energy Partner | 2023-12-25 | NA | 2025-06-25 | 3.8158 | Not Yet Certified | Data Not Available | Data Not Available | Data Not Available | Data Not Available | No | No | No | Pre-certification
SPQ0261 | PGE | PGE-2023-161 | Rodeo Solar | Pre-Certified | Conifer Energy Partners | Conifer Energy Partner | 2023-09-25 | NA | 2025-03-25 | 6.8092 | Not Yet Certified | Data Not Available | Data Not Available | Data Not Available | Data Not Available | No | No | No | 9/21/2023- Pre-certification
OCS034 | PAC | PP-2020-86 | Round Lake Solar | Certification | TLS Capital | Luminace | 2020-12-29 | 6/29/2022, 12/29/2022, 8/25/2023 | 2023-10-18 | 39.7039 | Not Yet Certified | 6/15/2022, 8/15/2022, 8/11/2023 | 2024-03-29 | 39.0132 | Yes | Yes | Yes; COVID-19, US Dept of Commerce investigation; | Yes; delayed utility timeline | 10/18/2023 - Certification
CSQ0001 | PGE | PGE-2020-10 | Sheridan Solar | Certification | Pacific Northwest Solar LLC | SolRiver Capital | 2022-05-25 | 2023-11-25 | 2024-05-25 | 22.8618 | Not Yet Certified | Data Not Available | Data Not Available | Data Not Available | Data Not Available | Yes | No | No | 3/9/2024 Cert Extension Request
CSQ0010 | PGE | PGE-2022-148 | Solar Harvest | Pre-Certified | Oregon Clean Power Cooperative | Oregon Clean Power Cooperative | 2022-10-10 | NA | 2024-04-10 | 18.3224 | Not Yet Certified | Not Applicable | 2023-05-15 | 7.1382 | No | No | No | No | Pre-certification
OCS047 | PAC | PP-2021-93 | Sunset Ridge Solar | Pre-Certified | Greenkey Solar | Luminace | 2021-04-20 | 10/22/2022, 4/20/2023, 6/20/2023, 10/20/2023, 12/14/2023 | 2024-06-11 | 36.0197 | Not Yet Certified | 12/15/2022, 9/22/2023 | 2024-08-23 | 40.1645 | Yes | Yes | Yes; COVID-19, US Dept of Commerce investigation; construction delays; | Yes; awaiting PPA; fiber optic material not ordered; IX design incomplete | 2/22/2024 - Cert Extension Request
OCS024 | PAC | PP-2020-81 | Tutuilla Solar | Pre-Certified | Sunthurst | Sunthurst | 2020-11-17 | 5/17/2022, 5/17/23, 11/17/2024 | 2024-11-17 | 41.0855 | Not Yet Certified | 12/30/2022, 5/25/2023 | 2025-09-30 | 58.4868 | Yes | No | Yes; land lease delays related to tribal relations | No | 6/23/2024- Cert Extension Request
532 | IP | IP-2020-72 | Verde Light Community Solar | Pre-Certified | Fleet Development | Fleet Development | 2020-06-16 | 6/16/2023, 3/16/2024 | 2024-08-01 | 46.1513 | Not Yet Certified | Not Applicable | 2024-05-14 | 46.9737 | No | No | Yes; Dept of Commerce investigation, awaiting grant funding; completing enrollment | No | 4/5/2024 - Cert Extension Request
SPQ0093 | PGE | PGE-2020-53 | Marquam Creek Solar LLC | Pre-Certified | Greenkey Solar | Luminace | 2022-04-15 | 2023-10-14 | 2024-10-31 | 24.1776 | Not Yet Certified | 2019-02-07 | 2024-08-31 | 28.5855 | Yes | Yes | Yes; contractor schedule constraints; inability to construct during winter | No | 8/26/2023 - Cert Extension Request
SPQ0179 | PGE | PGE-2020-18 | Waterford Solar | Pre-Certified | Solar Town | Luminace | 2022-05-02 | 2023-11-02 | 2024-08-31 | 23.6184 | Not Yet Certified | 2020-07-17 | 2024-07-26 | 26.8421 | In Negotiation | Yes | Yes; construction delays | Yes; unspecified | 8/26/2023- Cert Extension Request
OCS074 | PAC | PP-2021-126 | Wood River Solar | Pre-Certified | TLS Capital | TLS Capital | 2021-12-28 | 6/28/2023, 12/31/2023, 8/5/2024 | 2024-06-30 | 27.7303 | Not Yet Certified | Not Applicable | 2023-11-15 | 22.5987 | In Negotiation | No | Yes; equipment procurement, contractor schedule constraints | Yes; unspecified | 12/5/2023- Cert Extension Request
OCS064 | PAC | PP-2021-122 | McKinley Solar LLC | Pre-Certified | Sulus | Hawthorne Renewables | 2022-08-23 | 2024-02-23 | 2024-12-31 | 19.9013 | Not Yet Certified | 12/9/2022, 12/8/2023 | 2025-04-30 | 32.2697 | Yes | No | Yes; contractor schedule constraints | No | 10/13/2023 - Cert Extension Request
OCS061 | PAC | PP-2020-89 | Reservoir Solar LLC | Pre-Certified | Sulus | Hawthorne Renewables | 2022-04-15 | 2023-10-15 | 2024-12-31 | 24.1776 | Not Yet Certified | 3/3/2023, 4/19/2024 | 2025-03-28 | 35.4605 | Yes | Yes | Yes; construction contractor to be identified | No | 10/13/2023 - Cert Extension Request
OCS044 | PAC | PP-2021-116 | Cherry Creek Solar | Operational | TLS Capital | GreenKey Solar | 2021-07-27 | 2023-01-27 | 2023-05-16 | 32.7961 | 21.6447 | Not Applicable | 2022-10-18 | 14.7368 | Data Not Available | Yes | Yes; COVID-19, US Dept of Commerce investigation | No | NA
SPQ0181 | PGE | PGE-2020-45 | Sesqui-C Solar LLC | Operational | Conifer Energy Partners | HEP | 2020-06-12 | 12/12/2021, 6/12/2022, 12/12/2022 | 2022-12-14 | 46.2829 | 30.0987 | Not Applicable | 2021-12-07 | 17.8618 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation; participant enrollment | No | NA
SPQ0070 | PGE | PGE-2020-51 | Dunn Rd | Operational | Neighborhood Power | Neighborhood Power | 2020-06-22 | 2021-12-22 | 2021-03-01 | 45.9539 | 8.2895 | Data Not Available | Data Not Available | Data Not Available | Data Not Available | No | No | No | NA
SPQ0164 | PGE | PGE-2020-41 | Fruitland Creek Solar | Operational | TLS Capital | HEP | 2020-06-12 | 12/12/2021, 12/12/2022 | 2022-12-14 | 46.2829 | 30.0987 | Not Applicable | 2021-10-26 | 16.4803 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation | No | NA
OCS018 | PAC | PP-2021-110 | Hay Creek Solar | Operational | TLS Capital | TLS Capital | 2022-04-15 | 2023-10-15 | 2023-08-11 | 24.1776 | 15.8882 | 10/9/2021, 8/15/2022 | 2022-11-14 | 7.0066 | Data Not Available | No | No | No | NA
CSQ0002 | PGE | PGE-2020-70 | Jim and Salle's Place Apartments | Operational | Rose CDC | Rose CDC | 2020-04-21 | 10/21/2021, 4/21/2022 | 2022-06-13 | 47.9934 | 25.7566 | Data Not Available | Data Not Available | Data Not Available | Data Not Available | No | Yes; PPA delay | No | NA
SPQ0240 | PGE | PGE-2020-77 | Wallace Solar LLC | Pre-Certified | Sulus | SolRiver Capital | 2022-04-15 | 2023-10-15 | 2024-07-30 | 24.1776 | Not Yet Certified | 2023-05-31 | 2024-07-01 | 26.5789 | Yes | Yes | Yes; supply chain delays; permitting delays |  | 6/9/2023 - Cert Extension Request
SPQ0124 | PGE | PGE-2020-52 | Mt Hope Solar | Operational | Neighborhood Power | Neighborhood Power | 2020-06-22 | 2021-12-22 | 2021-03-01 | 45.9539 | 8.2895 | Data Not Available | Data Not Available | Data Not Available | Data Not Available | No | No | No | NA
OCS042 | PAC | PP-2020-78 | Oregon Shakespeare Festival Community Solar Project | Operational | Oregon Clean Power Cooperative | Oregon Clean Power Cooperative | 2020-11-03 | 2022-05-03 | 2022-03-16 | 41.5461 | 16.3816 | Not Applicable | 2021-07-30 | 8.8487 | Data Not Available | No | No | No | NA
SPQ0058 | PGE | PGE-2020-40 | Red Prairie Solar | Operational | TLS Capital | TLS Capital | 2020-03-11 | 2021-09-11 | 2021-10-19 | 49.3421 | 19.3092 | Data Not Available | Data Not Available | Data Not Available | Data Not Available | No | No | No | NA
SPQ0125 | PGE | PGE-2020-1 | River Valley | Operational | Neighborhood Power | Neighborhood Power | 2022-04-21 | 2023-10-21 | 2023-01-31 | 23.9803 | 9.375 | 2020-05-26 | 2022-03-25 | -0.88816 | Yes | No | No | No | NA
SPQ0071 | PGE | PGE-2020-38 | Sandy River Solar | Operational | TLS Capital | HEP | 2020-06-12 | 12/20/2021, 6/12/2022, 12/12/2022 | 2022-12-14 | 46.2829 | 30.0987 | Data Not Available | Data Not Available | Data Not Available | Data Not Available | Yes | Yes; COVID-19, US Dept of Commerce investigation | No | NA
SPQ0163 | PGE | PGE-2020-55 | Zena Solar LLC | Pre-Certified | Confier Energy Partners | UGEI | 2022-04-15 | 2023-10-15 | 2024-07-26 | 24.1776 | Not Yet Certified | 2022-03-04 | 2024-02-02 | 21.6447 | In Negotiation | Yes | Yes; construction delays | Yes; unspecified | 2/21/2024 - Cert Extension Request
SPQ0067 | PGE | PGE-2020-22 | Skyward Solar | Operational | Nautilus Solar | Standard Solar | 2020-03-11 | 9/1/2021, 7/1/2022, 1/1/2023 | 2022-12-01 | 49.3421 | 32.7303 | Data Not Available | Data Not Available | Data Not Available | Data Not Available | Yes | Yes; COVID-19, US Dept of Commerce investigation |  | NA
OCS005 | PAC | PP-2020-35 | Wallowa County Community Solar | Operational | Fleet Development | Fleet Development | 2020-03-25 | 2021-09-25 | 2022-06-30 | 48.8816 | 27.2039 | 6/4/2021 | 2021-12-30 | 21.2171 | Data Not Available | No | No | No | NA
OCS020 | PAC | PP-2021-92 | Whisky Creek Solar | Operational | TLS Capital | TLS Capital | 2021-04-20 | 10/20/2022, 6/12/2022, 12/12/2022 | 2023-07-06 | 36.0197 | 26.5461 | Not Applicable | 2022-08-15 | 15.8553 | Data Not Available | No | Yes; COVID-19, US Dept of Commerce investigation | No | NA
SPQ0166 | PGE | PGE-2020-48 | Williams Acres | Operational | Neighborhood Power | Neighborhood Power | 2020-06-22 | 2021-12-12 | 2021-04-05 | 45.9539 | 9.4408 | Data Not Available | Data Not Available | Data Not Available | Data Not Available | No | No | No | NA
OCS019 | PAC | PP-2020-85 | Wocus Marsh Solar | Operational | TLS Capital | TLS Capital | 2021-04-20 | 10/20/2022, 4/20/2023 | 2023-08-07 | 36.0197 | 27.5987 | 11/5/2021 | 2022-08-15 | 15.8553 | Data Not Available | No | Yes; US commerce investigation | No | NA

## OPUC Project Decisions
History of OPUC Decisions on CSP Project Recommendations
Interconnection Queue Number | CSP Project ID | CSP Project Name | Project Manager | Utility Service Area | Effective Date (day after comment period ends) | Link to PA Recommendation or Commission Decision in Docket No. UM 1930
OCS038 | PP-2021-112 | 7 Mile Solar | Sulus Solar | PAC | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS038 | PP-2021-112 | 7 Mile Solar | 7 Mile PM LLC | PAC | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
OCS038 | PP-2021-112 | 7 Mile Solar | 7 Mile PM LLC | PAC | 2024-02-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326626023.pdf
OCS046 | PP-2021-109 | Antelope Creek Solar | Antelope Creek PM LLC | PAC | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS046 | PP-2021-109 | Antelope Creek Solar | Antelope Creek PM LLC | PAC | 2023-11-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah16445.pdf
OCS046 | PP-2021-109 | Antelope Creek Solar | Antelope Creek PM, LLC | PAC | 2024-03-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326884032.pdf
SPQ0266 | PGE-2023-157 | Apricus Solar LLC | Conifer Community Energy 7 LLC | PGE | 2023-07-17 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah155245.pdf
SPQ0250 | PGE-2020-75 | Auburn Solar | Sulus Solar | PGE | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
SPQ0250 | PGE-2020-75 | Auburn Solar | Sulus Solar | PGE | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
SPQ0250 | PGE-2020-75 | Auburn Solar | Auburn Solar LLC | PGE | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
SPQ0186 | PGE-2020-15 | Belvedere Solar | Solar Town LLC | PGE | 2022-07-14 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah154054.pdf
SPQ0186 | PGE-2020-15 | Belvedere Solar | Solar Town LLC | PGE | 2022-07-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah82827.pdf
SPQ0186 | PGE-2020-15 | Belvedere Solar | Solar Town | PGE | 2022-11-11 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah10130.pdf
SPQ0186 | PGE-2020-15 | Belvedere Solar | Solar Town | PGE | 2023-08-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145613.pdf
SPQ0186 | PGE-2020-15 | Belvedere Solar | Solar Town | PGE | 2023-08-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145421.pdf
OCS055 | PP-2021-125 | Blackwell Creek Solar | Blackwell Creek PM LLC | PAC | 2022-12-01 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah152218.pdf
62 | PP-2021-104 | Buckaroo Solar 1 LLC | Buckaroo Solar 1 LLC | PAC | 2022-05-02 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah162612.pdf
62 | PP-2021-104 | Buckaroo Solar 1 LLC | Buckaroo Solar 1 LLC | PAC | 2024-04-04 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah327471032.pdf
63 | PP-2021-103 | Buckaroo Solar 2 | Buckaroo Solar 2 LLC | PAC | 2022-05-02 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah162612.pdf
63 | PP-2021-103 | Buckaroo Solar 2 | Buckaroo Solar 2 LLC | PAC | 2024-04-04 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah327471032.pdf
SPQ0191 | PGE-2020-21 | Buckner Creek Solar LLC | Conifer Community Energy LLC | PGE | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
SPQ0191 | PGE-2020-21 | Buckner Creek Solar LLC | Conifer Community Energy LLC | PGE | 2023-10-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15137.pdf
OCS041 | PP-2021-95 | Burg Solar | Sulus Solar | PAC | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS041 | PP-2021-95 | Burg Solar | Sulus Solar | PAC | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
CSPQ008 | PP-2020-76 | Burlingame Solar LLC | Sulus Solar | PAC | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
CSPQ008 | PP-2020-76 | Burlingame Solar LLC | Burlingame Solar LLC | PAC | 2022-07-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah132928.pdf
OCS050 | PP-2021-94 | Canyonville Solar 1 | Sulus Solar | PAC | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS050 | PP-2021-94 | Canyonville Solar 1 | Canyonville Solar 1 LLC | PAC | 2023-06-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah14537.pdf
OCS050 | PP-2021-94 | Canyonville Solar 1 | Sulus Solar | PAC | 2022-05-11 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah94645.pdf
OCS051 | PP-2022-142 | Canyonville Solar 2 | Sulus Solar | PAC | 2022-05-11 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah94645.pdf
OCS051 | PP-2022-142 | Canyonville Solar 2 | Sulus Solar | PAC | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS051 | PP-2022-142 | Canyonville Solar 2 | Canyonville Solar 2 LLC | PAC | 2023-06-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah14537.pdf
SPQ0158 | PGE-2020-56 | Carnes Creek Solar LLC | Conifer Community Energy 5, LLC | PGE | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
SPQ0158 | PGE-2020-56 | Carnes Creek Solar LLC | Conifer Community Energy 5 LLC | PGE | 2023-01-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah93220.pdf
OCS049 | PP-2021-113 | Chapman Creek Solar | Chapman Creek PM LLC | PAC | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS049 | PP-2021-113 | Chapman Creek Solar | Chapman Creek PM LLC | PAC | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
OCS044 | PP-2021-116 | Cherry Creek Solar | Cherry Creek Project Manager LLC | PAC | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS044 | PP-2021-116 | Cherry Creek Solar | Cherry Creek Project Manager LLC | PAC | 2023-04-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah111830.pdf
SPQ0180 | PGE-2020-17 | Clayfield Solar LLC | Solar Town LLC | PGE | 2022-07-14 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah154054.pdf
SPQ0180 | PGE-2020-17 | Clayfield Solar LLC | Solar Town LLC | PGE | 2022-11-11 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah10130.pdf
SPQ0180 | PGE-2020-17 | Clayfield Solar LLC | Solar Town LLC | PGE | 2023-08-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145613.pdf
SPQ0180 | PGE-2020-17 | Clayfield Solar LLC | Solar Town LLC | PGE | 2023-08-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145421.pdf
OCS058 | PP-2021-121 | Coker Solar | Sulus Solar | PAC | 2022-12-01 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah152218.pdf
OCS058 | PP-2021-121 | Coker Solar | Sulus Solar | PAC | 2023-09-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah122749.pdf
SPQ0220 | PGE-2020-11 | Cork Solar | Solar Town | PGE | 2023-08-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145613.pdf
SPQ0220 | PGE-2020-11 | Cork Solar LLC | Solar Town LLC | PGE | 2022-05-02 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah162612.pdf
SPQ0220 | PGE-2020-11 | Cork Solar LLC | Solar Town | PGE | 2023-08-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145421.pdf
SPQ0152 | PGE-2020-34 | Cosper Creek Solar LLC | Conifer Community Energy 1 LLC | PGE | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
SPQ0152 | PGE-2020-34 | Cosper Creek Solar LLC | Conifer Community Energy 1 LLC | PGE | 2023-01-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah93220.pdf
SPQ0193 | PGE-2020-19 | Dover Solar | Solar Town LLC | PGE | 2022-07-14 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah154054.pdf
SPQ0193 | PGE-2020-19 | Dover Solar | Solar Town LLC | PGE | 2022-07-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah82827.pdf
SPQ0193 | PGE-2020-19 | Dover Solar | Solar Town | PGE | 2022-11-11 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah10130.pdf
SPQ0193 | PGE-2020-19 | Dover Solar | Solar Town | PGE | 2023-08-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145613.pdf
SPQ0193 | PGE-2020-19 | Dover Solar | Luminace | PGE | 2024-04-04 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah327471032.pdf
SPQ0164 | PGE-2020-41 | Fruitland Creek Solar | FC PM LLC | PGE | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
SPQ0164 | PGE-2020-41 | Fruitland Creek Solar | FC PM LLC | PGE | 2023-01-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah93220.pdf
OCS012 | PP-2020-63 | Goodling Annex | Bonneville Environmental Foundation | PAC | 2022-06-29 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah102926.pdf
OCS012 | PP-2020-63 | Goodling Annex | Bonneville Environmental Foundation | PAC | 2023-06-30 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah152441.pdf
OCS012 | PP-2020-63 | Goodling Annex | Bonneville Environmental Foundation | PAC | 2024-04-04 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah327471032.pdf
OCS045 | PP-2021-99 | Green Solar | Sulus Solar | PAC | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS045 | PP-2021-99 | Green Solar | Sulus Solar | PAC | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS045 | PP-2021-99 | Green Solar | Green Solar LLC | PAC | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
SPQ0157 | PGE-2020-37 | Gun Club Solar LLC | Conifer Community Energy 2 LLC | PGE | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
SPQ0157 | PGE-2020-37 | Gun Club Solar LLC | Conifer Community Energy 2 LLC | PGE | 2023-08-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145236.pdf
OCS018 | PP-2021-110 | Hay Creek Solar | Hay Creek PM LLC | PAC | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS018 | PP-2021-110 | Hay Creek Solar | Hay Creek PM LLC | PAC | 2023-04-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah111830.pdf
OCS018 | PP-2021-110 | Hay Creek Solar | Hay Creek PM LLC | PAC | 2023-06-30 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah152727.pdf
CSQ0002 | PGE-2020-70 | Jim and Salle's Place Apartments | ROSE Community Development | PGE | 2022-03-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah121349.pdf
SPQ0094 | PGE-2020-42 | Kaiser Creek Solar LLC | Kaiser Creek Project Manager LLC | PGE | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
SPQ0094 | PGE-2020-42 | Kaiser Creek Solar LLC | Kaiser Creek Project Manager LLC | PGE | 2023-06-19 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah173011.pdf
OCS039 | PP-2021-97 | Kelly Creek Solar | Kelly Creek Project Manager LLC | PAC | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS039 | PP-2021-97 | Kelly Creek Solar | Kelly Creek Project Manager LLC | PAC | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
SPQ0272 | PGE-2023-167 | Lincoln Solar LLC | CCE 9 LLC | PGE | 2023-12-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah325483023.pdf
SPQ0272 | PGE-2023-167 | Lincoln Solar LLC | CCE 9 LLC | PGE | 2023-12-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah325483023.pdf
OCS025 | PP-2020-80 | Linkville Solar | Linkville PM LLC | PAC | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS025 | PP-2020-80 | Linkville Solar | Linkville PM LLC | PAC | 2023-06-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah14537.pdf
SPQ0182 | PGE-2020-16 | Manchester Solar | Solar Town LLC | PGE | 2022-07-14 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah154054.pdf
SPQ0182 | PGE-2020-16 | Manchester Solar | Solar Town | PGE | 2022-11-11 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah10130.pdf
SPQ0182 | PGE-2020-16 | Manchester Solar | Solar Town | PGE | 2023-08-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145751.pdf
SPQ0182 | PGE-2020-16 | Manchester Solar | Solar Town | PGE | 2023-09-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah123054.pdf
SPQ0182 | PGE-2020-16 | Manchester Solar LLC | Manchester Solar LLC | PGE | 2024-03-05 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326851023.pdf
OCS027 | PP-2020-82 | Marble Solar | Marble Solar LLC | PAC | 2023-06-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah14537.pdf
OCS027 | PP-2020-82 | Marble Solar LLC | Sulus Solar | PAC | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS027 | PP-2020-82 | Marble Solar LLC | Marble Solar LLC | PAC | 2022-07-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah132928.pdf
SPQ0093 | PGE-2020-53 | Marquam Creek Solar LLC | Marquam Creek Project Manager LLC | PGE | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
SPQ0093 | PGE-2020-53 | Marquam Creek Solar LLC | Marquam Creek Project Manager LLC | PGE | 2023-08-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145236.pdf
OCS064 | PP-2021-122 | McKinley Solar LLC | Sulus Solar | PAC | 2022-08-23 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah124853.pdf
OCS064 | PP-2021-122 | McKinley Solar LLC | Sulus Solar | PAC | 2023-09-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah122749.pdf
OCS064 | PP-2021-122 | McKinley Solar LLC | Sulus Solar | PAC | 2023-10-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15137.pdf
CSQ0004 | PGE-2021-115 | Mompano Solar | Mompano Solar Project Manager LLC | PGE | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
CSQ0004 | PGE-2021-115 | Mompano Solar | Mompano Solar Project Manager LLC | PGE | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
OCS035 | PP-2021-111 | Orchard Knob Solar | Orchard Knob Solar LLC | PAC | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS035 | PP-2021-111 | Orchard Knob Solar | Orchard Knob PM LLC | PAC | 2023-11-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah16445.pdf
OCS035 | PP-2021-111 | Orchard Knob Solar | Orchard Knob PM, LLC | PAC | 2024-03-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326884032.pdf
OCS057 | PP-2020-88 | Perrydale Solar | Sulus Solar | PAC | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS057 | PP-2020-88 | Perrydale Solar | Sulus Solar | PAC | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS057 | PP-2020-88 | Perrydale Solar | Perrydale Solar LLC | PAC | 2024-01-05 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah325686023.pdf
Q0666 | PP-2020-13 | Pilot Rock Solar 1 | Pilot Rock Solar 1 LLC | PAC | 2023-08-17 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah133441.pdf
1045 | PP-2020-71 | Pilot Rock Solar 2 | Pilot Rock Solar 2 LLC | PAC | 2023-08-17 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah133441.pdf
OCS036 | PP-2020-84 | Pine Grove Solar | Pine Grove PM LLC | PAC | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS036 | PP-2020-84 | Pine Grove Solar | Pine Grove PM LLC | PAC | 2022-10-20 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15575.pdf
OCS036 | PP-2020-84 | Pine Grove Solar | Pine Grove PM LLC | PAC | 2023-10-18 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau154953.pdf
SPQ0058 | PGE-2020-40 | Red Prairie Solar | RP PM LLC | PGE | 2022-10-20 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah16130.pdf
OCS061 | PP-2020-89 | Reservoir Solar LLC | Sulus Solar | PAC | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS061 | PP-2020-89 | Reservoir Solar LLC | Sulus Solar | PAC | 2023-09-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah122749.pdf
OCS061 | PP-2020-89 | Reservoir Solar LLC | Sulus Solar | PAC | 2023-10-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15137.pdf
SPQ0125 | PGE-2020-1 | River Valley | Neighborhood Power | PGE | 2022-04-21 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah165930.pdf
SPQ0261 | PGE-2023-161 | Rodeo Solar | Conifer Community Energy 8 LLC | PGE | 2023-09-21 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164944.pdf
OCS034 | PP-2020-86 | Round Lake Solar | Round Lake PM LLC | PAC | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS034 | PP-2020-86 | Round Lake Solar | Round Lake PM LLC | PAC | 2022-10-20 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15575.pdf
OCS034 | PP-2020-86 | Round Lake Solar | Round Lake PM LLC | PAC | 2023-10-18 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau154953.pdf
SPQ0071 | PGE-2020-38 | Sandy River Solar | SR PM LLC | PGE | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
SPQ0071 | PGE-2020-38 | Sandy River Solar | Sandy River Solar LLC | PGE | 2023-06-19 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah173011.pdf
SPQ0181 | PGE-2020-45 | Sesqui-C Solar LLC | Sesqui-C Solar | PGE | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
SPQ0181 | PGE-2020-45 | Sesqui-C Solar LLC | Conifer Community Energy 3 LLC | PGE | 2023-01-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah93220.pdf
CSQ0001 | PGE-2020-10 | Sheridan Solar | Pacific Northwest Solar LLC | PGE | 2022-05-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164915.pdf
CSQ0001 | PGE-2020-10 | Sheridan Solar | Pacific Northwest Solar LLC | PGE | 2022-09-06 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah95135.pdf
CSQ0001 | PGE-2020-10 | Sheridan Solar | Sheridan Solar LLC | PGE | 2024-03-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326908023.pdf
SPQ0067 | PGE-2020-22 | Skyward Solar | Skyward Solar LLC | PGE | 2022-07-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah82552.pdf
CSQ0010 | PGE-2022-148 | Solar Harvest | Oregon Clean Power Cooperative | PGE | 2022-10-10 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah104356.pdf
OCS047 | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge Project Manager LLC | PAC | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS047 | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge Project Manager LLC | PAC | 2023-05-24 | https://edocs.puc.state.or.us/efdocs/HAC/um1930hac154159.pdf
OCS047 | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge PM LLC | PAC | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
OCS047 | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge Project Manager, LLC | PAC | 2024-02-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326626023.pdf
OCS026 | PP-2020-87 | Taylor Solar | Sulus Solar | PAC | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS026 | PP-2020-87 | Taylor Solar | Sulus Solar | PAC | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
24 | PP-2020-81 | Tutuilla Solar | Tutuilla Solar LLC | PAC | 2022-06-29 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah163116.pdf
532 | IP-2020-72 | Verde Light Community Solar | Fleet Development LLC | IP | 2022-06-29 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah161013.pdf
532 | IP-2020-72 | Verde Light Community Solar | Fleet Development LLC | IP | 2023-06-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah14537.pdf
532 | IP-2020-72 | Verde Light Community Solar | Fleet Development LLC | IP | 2023-08-17 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah133250.pdf
532 | IP-2020-72 | Verde Light Community Solar | Fleet Development LLC | IP | 2024-04-04 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah327471032.pdf
SPQ0240 | PGE-2020-77 | Wallace Solar | Wallace Solar LLC | PGE | 2023-06-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah14537.pdf
SPQ0240 | PGE-2020-77 | Wallace Solar LLC | Sulus Solar | PGE | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
SPQ0240 | PGE-2020-77 | Wallace Solar LLC | Sulus Solar | PGE | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS005 | PP-2020-35 | Wallowa County Community Solar | Fleet Development LLC | PAC | 2022-08-23 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah133619.pdf
SPQ0179 | PGE-2020-18 | Waterford Solar | Solar Town LLC | PGE | 2022-05-02 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah162612.pdf
SPQ0179 | PGE-2020-18 | Waterford Solar | Solar Town | PGE | 2023-08-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145421.pdf
SPQ0179 | PGE-2020-18 | Waterford Solar | Solar Town | PGE | 2023-08-28 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145613.pdf
OCS037 | PP-2021-91 | Wayland Solar LLC | Sulus Solar | PAC | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS037 | PP-2021-91 | Wayland Solar LLC | Wayland Solar LLC | PAC | 2022-07-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah132928.pdf
OCS020 | PP-2021-92 | Whisky Creek Solar | Whisky Creek PM LLC | PAC | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS020 | PP-2021-92 | Whisky Creek Solar | Whisky Creek PM LLC | PAC | 2023-06-30 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah152727.pdf
OCS020 | PP-2021-92 | Whisky CreekSolar | Whisky Creek PM LLC | PAC | 2023-04-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah111830.pdf
OCS019 | PP-2020-85 | Wocus Marsh | Wocus Marsh PM LLC | PAC | 2023-06-30 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah152727.pdf
OCS019 | PP-2020-85 | Wocus Marsh Solar | Wocus Marsh PM LLC | PAC | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS019 | PP-2020-85 | Wocus Marsh Solar | Wocus Marsh PM LLC | PAC | 2023-04-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah111830.pdf
OCS074 | PP-2021-126 | Wood River Solar | Wood River PM LLC | PAC | 2023-08-17 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah13247.pdf
OCS074 | PP-2021-126 | Wood River Solar | Wood River PM, LLC | PAC | 2023-12-19 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah325686023.pdf
OCS074 | PP-2021-126 | Wood River Solar | Wood River PM LLC | PAC | 2024-01-05 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah325686023.pdf
SPQ0163 | PGE-2020-55 | Zena Solar LLC | Conifer Community Energy 6 LLC | PGE | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
SPQ0163 | PGE-2020-55 | Zena Solar LLC | Conifer Community Energy 6 LLC | PGE | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
SPQ0163 | PGE-2020-55 | Zena Solar LLC | Zena Solar, LLC | PGE | 2024-02-21 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326608023.pdf