## Executive Summary
| February 2025 Monthly Project Progress Report |  | Questions or feedback? Contact the CSP Program Administrator at info@oregoncsp.org
Executive Summary |  | Project Status Changes Since January 2025 report
|  | Utility | # of Pre-Certified Projects | # of Certified Projects | # of Operational Projects | # of Operational Date Extensions | # of Projects granted Certification Extensions
|  | IP | 0 | 0 | 0 | 0 | 0
|  | PAC | 0 | 1 | 2 | 0 | 0
|  | PGE | 0 | 1 | 0 | 0 | 0
|  | Total | 0 | 2 | 2 | 0 | 0
Status of all CSP Projects
|  |  | Pre-Certified | Certified | Operational
|  | Utility | # of Pre-Certified Projects | Pre-Certified Project Capacity (MW) | # of Certified Projects | Certified Project Capacity (MW) | # of Operational Projects | Operational Project Capacity (MW) | Total Projects in Program | Total Capacity (MW) in Program
|  | IP | 0 | 0 | 0 | 0 | 1 | 2.95 | 1 | 2.95
|  | PAC | 17 | 27.85 | 4 | 9.12 | 14 | 16.72 | 35 | 53.69
|  | PGE | 9 | 19.57 | 2 | 5.47 | 23 | 48.64 | 34 | 73.68
|  | Total | 26 | 47.42 | 6 | 14.59 | 38 | 68.31 | 70 | 130.32
Viewing Project Data in this Report |  | Additional Project Statistics (Cumulative)
|  | Utility | Avg # of Months Since Pre-Certification (Pre-Certified & Certified Projects) | # of Projects with Ownership Tranfers | # of Projects Granted Certification Extensions | # of Projects Citing Development Delays* | # of Projects Citing Interconnection Delays*
|  | IP | 48 | 0 | 1 | 1 | 0
|  | PAC | 32 | 20 | 17 | 16 | 11
|  | PGE | 24 | 20 | 16 | 16 | 5
|  | Total | NA | 40 | 34 | 33 | 16
*based on information provided by Project Managers in requests for Certification extensions.
This report includes two additional project data tables accessible via the tabs below that include specific project data and that allow users to filter on a range of specific parameters. Due to constraints in Microsoft Word, the tabs cannot be sorted by those parameters.
CSP Project Data This sheet provides a range of specific data for all Pre-Certified, Certified and Operational projects in the Program. Each column in the table allows for users to sort the projects on specific parameters.
OPUC Project Decisions This sheet includes the history of OPUC decisions for CSP projects, beginning with Pre-Certification and through Certification. Users can sort on a range of parameters and access PA recommendations and Commission decisions that have been posted to Docket No. UM 1930.
The Community Solar Program Administrator (PA) began producing monthly-updated CSP project progress reports in April 2024. The February 2025 report is the eleventh monthly report. The PA and OPUC Staff intend for the reports to provide all parties with timely and updated information for tracking project progress, with a focus on identifying and mitigating avoidable delays, increasing transparency and accountability, and improving Program performance. The reports are an important next step in OPUC Staff's broader plan to diminish additional project development and interconnection delays.
Project Updates since the December 2024 report (1/19/25 - 2/18/25):
One project in PGE became Certified.
One project in PGE was granted a Certification extension.
One additional project in PGE is currently under COD negotiations with the utility.
Two projects in PAC became operational.
One project in PAC became Certified.
Three projects in PAC were canceled; two carve-out projects and one general market project.
Two projects in PAC amended their COD.
Four new columns added to "Status of all CSP Projects" table: Pre-Certified Project Capacity (MW), Certified Project Capacity (MW), Operational Project Capacity (MW), and Total Capacity (MW) in Program
The PA welcomes stakeholder input and suggestions to make the report increasingly valuable and effective in support of improving overall Program performance. Comments, questions, and feedback can be directed to administrator@oregoncsp.org.

## CSP Project Data
2025-02-21
|  |  | CSP Project Data | [12 empty] | CSP Project Data | [6 empty] | any c
|  |  |  | Highlighted rows indicate update to Project since previous report. See Column Y for details. | [12 empty] | Highlighted rows indicate update to Project since previous report. See Column Y for details.
Utility Queue Number | Utility Service Area | CSP Project ID | Project Name | CSP Project Status | Initial owner entity/parent owner entity | Current owner entity/parent owner entity | Capacity Tier | Carve-out Eligible? | Total Capacity (kW-AC) | Pre-Certification Date | Prior Certification Deadlines | Current Certification Deadline (Pre-Certified projects) | Date Certified (Certified and Operational Projects) | Months Since Pre-Certification (Pre-certified & Certified Projects Only) | Operational Date | Months from Pre-Certification to Certification (Operational Projects Only) | Prior Commercial Operating Date(s) (COD) - Utility Provided | Current COD - Utility Provided | Months from Pre-Certification to Current COD - Utility Provided | Is the applicant currently engaged in negotiating a revised COD with the Utility? - Utility Provided | History of Parent Entity Ownership transfers? | History of Project Development Delays? (Based Only on Project Reporting) | History of Interconnection Delays? (Based Only on Project Reporting) | Most Recent Project Recommendation Posted to Docket No. UM 1930 | Updates since last report | Cert. Extension | Dev Delay | IX Delay
OCS038 | PAC | PP-2021-112 | 7 Mile Solar | Pre-Certified | TLS Capital | Luminace | 2 | No | 951 | 2022-04-15 | 10/15/2023, 12/14/2023, 6/11/2024 | 2025-01-17 | Not Yet Certified | 34.3092 | Not Yet Operational | Not Yet Certified | 8/15/2022, 12/9/2022, 7/21/2023 | 2024-09-27 | 29 | Yes | Yes | Yes; construction delays | Yes; IX work incomplete- fiber optic material not ordered; IX design incomplete; IX redesign, IX study incomplete, IX work incomplete; order IX materials | 7/24/2024 - Cert Extension Request | None | None | None | None
OCS071 | PAC | PP-2024-185 | Almon Solar | Pre-Certified | Hawthorne Renewables LLC | Evergreen | 2 | Yes | 1375 | 2024-11-08 | NA | 2026-05-08 | Not Yet Certified | 3.4539 | Not Yet Operational | Not Yet Certified | Not Applicable | Data Not Available | Data Not Available | Yes | Yes | No | No | 11/8/2024 - Pre-Certification | None | None | None | None
OCS046 | PAC | PP-2021-109 | Antelope Creek Solar | Operational | TLS Capital | Luminace | 2 | No | 2250 | 2022-04-15 | 10/15/2023, 1/15/2024 | Operational | 2024-06-12 | Operational | 2024-09-20 | 26 | 8/15/2022, 12/16/2022, 7/28/2023 | 2024-06-21 | 26 | No | Yes | Yes; low-income enrollment incomplete | Yes; IX work incomplete | 6/12/2024 - Certification | None | None | None | None
SPQ0266 | PGE | PGE-2023-157 | Apricus Solar LLC | Pre-Certified | Conifer Energy Partners | Kendall Sustainable Infrastructure | 2 | No | 2500 | 2023-07-15 | 2025-01-15 | 2025-04-16 | Not Yet Certified | 19.3092 | Not Yet Operational | Not Yet Certified | 2025-06-16 | 2025-07-18 | 24 | Yes | Yes | No | No | 10/24/2023 - Cert Extension Request | None | None | None | None
SPQ0250 | PGE | PGE-2020-75 | Auburn Solar | Operational | Sulus | SolRiver Capital | 2 | No | 2970 | 2022-04-15 | 10/15/2023, 4/15/2024 | Operational | 2024-06-25 | Operational | 2024-07-01 | 26 | 2022-06-15 | 2023-12-15 | 20 | No | Yes | Yes; equipment procurement | Yes; unspecified | 6/25/2024 - Certification | None | None | None | None
SPQ0186 | PGE | PGE-2020-15 | Belvedere Solar | Operational | SPI | Luminace | 1 | No | 2970 | 2020-04-27 | 2/7/2022, 8/7/2022, 2/7/2023, 8/7/2023, 8/19/2024 | Operational | 2024-12-11 | Operational | 2024-12-16 | 56 | 6/21/2021, 9/15/2023 | 2024-07-26 | 51 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation; | Yes; IX construction delays | 12/11/2024 - Certification | None | None | None | None
OCS055 | PAC | PP-2021-125 | Blackwell Creek Solar | Operational | TLS Capital | TLS Capital | 2 | No | 1350 | 2022-12-01 | NA | Operational | 2024-07-10 | Operational | 2025-01-08 | 19 | 2023-10-27 | 2024-05-22 | 18 | No | No | No | No | 7/10/2024- Certification | None | None | None | None
CSQ0015 | PGE | PGE-2024-177 | Bradley Solar 2 | Pre-Certified | Hawthorne Renewables LLC | Hawthorne Renewables LLC | 2 | No | 1000 | 2024-05-17 | NA | 2025-11-17 | Not Yet Certified | 9.2105 | Not Yet Operational | Not Yet Certified | Not Applicable | 2026-12-30 | 31 | No | No | No | No | 5/17/2024 - Pre-Certification | None | None | None | None
OCS062 | PAC | PP-2021-104 | Buckaroo Solar 1 LLC | Pre-Certified | Sunthurst | Sunthurst | 2 | No | 2400 | 2022-04-30 | 2023-11-23 | 2025-09-25 | Not Yet Certified | 33.8158 | Not Yet Operational | Not Yet Certified | 7/21/2023, 6/28/2024 | 2025-09-30 | 41 | No | No | Yes; COVID-19, US Dept of Commerce investigation; construction delays; | Yes; revised interconnection schedule | 4/5/2024- Cert Extension Request | None | None | None | None
OCS063 | PAC | PP-2021-103 | Buckaroo Solar 2 | Pre-Certified | Sunthurst | Sunthurst | 2 | No | 2990 | 2022-04-30 | 2023-11-23 | 2025-09-30 | Not Yet Certified | 33.8158 | Not Yet Operational | Not Yet Certified | 2023-07-21 | 2025-09-30 | 41 | No | No | Yes; COVID-19, US Dept of Commerce investigation; construction delays; | Yes; revised interconnection schedule | 4/5/2024- Cert Extension Request | None | None | None | None
SPQ0191 | PGE | PGE-2020-21 | Buckner Creek Solar LLC | Certified | Conifer Energy Partners | Luminace | 2 | No | 2500 | 2022-04-15 | 2023-08-15 | 2024-12-31 | 2024-12-11 | 34.3092 | Not Yet Operational | 32 | 11/30/2020, 11/15/2023 | 2024-12-04 | 32 | No | No | Yes; contractor schedule constraints; inability to construct during winter | No | 12/11/2024 - Certification | None | None | None | None
OCS041 | PAC | PP-2021-95 | Burg Solar | Pre-Certified | Sulus | TLS Capital | 2 | No | 1500 | 2022-04-15 | 2023-10-15 | 2024-09-30 | Not Yet Certified | 34.3092 | Not Yet Operational | Not Yet Certified | 9/23/2022 | 2024-12-06 | 32 | Yes | Yes | No | No | 6/3/2023 - PM Transfer | None | None | None | None
OCS008 | PAC | PP-2020-76 | Burlingame Solar LLC | Pre-Certified | Sulus | GreenKey Solar | 1 | No | 2125 | 2020-12-29 | 12/29/2023, 6/29/2022, 6/30/2023 | 2024-09-30 | Not Yet Certified | 49.8355 | Not Yet Operational | Not Yet Certified | 5/17/2022, 3/17/2022 | 2024-09-06 | 44 | Yes | Yes | Yes; US Dept of Commerce investigation; uncertainty of Tier 2 capacity release | No | 7/27/2022 - Cert Extension Request | None | None | None | None
OCS050 | PAC | PP-2021-94 | Canyonville Solar 1 | Pre-Certified | Sulus | SolRiver Capital | 2 | No | 1000 | 2022-05-11 | 11/11/2023, 9/11/2024 | 2026-06-26 | Not Yet Certified | 33.4539 | Not Yet Operational | Not Yet Certified | 11/4/2022, 6/23/2023 | 2026-05-22 | 48 | No | Yes | Yes; supply chain delays | Yes; waiting for revised IX timeline from PAC | 11/9/2024 - Cert Extension Request | None | None | None | None
OCS051 | PAC | PP-2022-142 | Canyonville Solar 2 | Pre-Certified | Sulus | SolRiver Capital | 2 | No | 1500 | 2022-05-11 | 11/12/2023, 9/11/2024 | 2026-06-26 | Not Yet Certified | 33.4539 | Not Yet Operational | Not Yet Certified | 11/4/2022, 6/23/2023 | 2026-05-22 | 48 | No | Yes | Yes; supply chain delays | Yes; waiting for revised IX timeline from PAC | 11/9/2024 - Cert Extension Request | None | None | None | None
SPQ0158 | PGE | PGE-2020-56 | Carnes Creek Solar LLC | Operational | Conifer Energy Partners | HEP | 1 | No | 2500 | 2020-04-27 | 12/12/2021, 6/12/2022 | Operational | 2022-11-30 | Operational | 2022-12-15 | 31 | 1/25/2021, 3/31/2021 | 2022-12-13 | 32 | No | No | Yes; COVID-19, US Dept of Commerce investigation | No | NA | None | None | None | None
C3-014 | PAC | PP-2024-175 | Chaberton Solar Diamond Peak LLC | CANCELED | Chaberton Energy | Chaberton Energy | 2 | Yes | 2500 | 2024-09-24 | 2026-03-24 | Cancelled | Not Yet Certified | 4.9342 | Not Yet Operational | Not Applicable | Not Applicable | 2025-07-30 | 10 | No | No | No | No | 9/24/2024 - Pre-Certification | CANCELED | None | None | None
C3-178 | PAC | PP-2024-176 | Chaberton Solar Horthorn Rim LLC | CANCELED | Chaberton Energy | Chaberton Energy | 2 | Yes | 2999 | 2024-09-24 | 2026-03-24 | Cancelled | Not Yet Certified | 4.9342 | Not Yet Operational | Not Applicable | Not Applicable | 2025-07-30 | 10 | No | No | No | No | 9/24/2024 - Pre-Certification | CANCELED | None | None | None
OCS049 | PAC | PP-2021-113 | Chapman Creek Solar | Certified | TLS Capital | Luminace | 2 | No | 2990 | 2022-04-15 | 10/15/2023, 10/15/2024 | 2024-12-31 | 2024-12-11 | 34.3092 | Not Yet Operational | 32 | 11/30/2022, 10/31/2023 | 2024-10-18 | 30 | Yes | Yes | Yes; contractor schedule constraints; inability to construct during winter | Yes; unspecified | 12/11/2024 - Certification | None | None | None | None
OCS044 | PAC | PP-2021-116 | Cherry Creek Solar | Operational | TLS Capital | GreenKey Solar | 1 | Yes | 359 | 2021-07-29 | 2023-01-27 | Operational | 2022-12-14 | Operational | 2023-05-17 | 17 | Not Applicable | 2022-10-18 | 15 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation | No | NA | None | None | None | None
SPQ0180 | PGE | PGE-2020-17 | Clayfield Solar LLC | Operational | Solar Town | Luminace | 1 | No | 2565 | 2020-04-27 | 1/17/2023, 7/17/2023, 6/30/2024 | Operational | 2024-10-30 | Operational | 2024-11-01 | 54 | 3/26/2021, 2/15/2022 | 2024-07-24 | 51 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation, timeline changes due to federal ITC | Yes; IX construction delays | 10/30/2024 - Certification | None | 1 | 1 | 1
OCS058 | PAC | PP-2021-121 | Coker Solar | Pre-Certified | Sulus | Hawthorne Renewables LLC | 2 | No | 1250 | 2022-12-01 | 2024-06-01 | 2025-08-30 | Not Yet Certified | 26.7434 | Not Yet Operational | Not Yet Certified | 3/24/2023, 3/22/2024 | 2025-05-30 | 30 | Yes | Yes | Yes; project financing delays | No | 11/9/2024 - Cert Extension Request | None |  | 1
OCS067 | PAC | PP-2022-138 | Colfax Solar | Pre-Certified | Hawthorne Renewables LLC | Hawthorne Renewables LLC | 2 | No | 1000 | 2024-11-23 | NA | 2026-05-23 | Not Yet Certified | 2.9605 | Not Yet Operational | Not Yet Certified | Not Applicable | Data Not Available | Not Applicable | Yes | No | No | No | 11/23/2024 - Pre-certification | None
SPQ0220 | PGE | PGE-2020-11 | Cork Solar LLC | Operational | Solar Town | Luminace | 2 | No | 1260 | 2022-04-30 | 10/30/2023, 8/30/2024 | Operational | 2024-12-11 | Operational | 2024-12-16 | 31 | 6/4/2021, 10/23/2023 | 2024-09-26 | 29 | No | Yes | Yes; construction delays | Yes; IX construction delays | 12/11/2024 - Certification | None | 1 | 1 | 1
SPQ0152 | PGE | PGE-2020-34 | Cosper Creek Solar LLC | Operational | TLS Capital | HEP | 1 | No | 2500 | 2020-04-27 | 12/12/2021, 6/12/2022, 12/12/2022 | Operational | 2022-11-30 | Operational | 2022-12-15 | 31 | 2020-07-06 | 2021-06-01 | 13 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation | No | NA | None | 1 | 1
CSQ0014 | PGE | PGE-2024-180 | CP Sheridan | Pre-Certified | ClearPath | ClearPath | 2 | Yes | 2800 | 2024-05-31 | NA | 2025-12-01 | Not Yet Certified | 8.75 | Not Yet Operational | Not Yet Certified | Not Applicable | 2025-08-25 | 15 | Yes | No | No | No | NA | None
SPQ0262 | PGE | PGE-2024-183 | Crawford Solar | Pre-Certified | Hawthorne Renewables LLC | Hawthorne Renewables LLC | 2 | No | 2750 | 2024-10-24 | NA | 2026-04-24 | Not Yet Certified | 3.9474 | Not Yet Operational | Not Yet Certified | Not Applicable | Data Not Available | Data Not Available | Yes | No | No | No | 10/23/2024 - Pre-Certification | None
SPQ0193 | PGE | PGE-2020-19 | Dover Solar | Operational | Solar Town | Luminace | 1 | No | 1980 | 2020-04-27 | 2/1/2022, 8/1/2022, 7/1/2023, 2/29/2024, 8/27/2024 | Operational | 2024-12-11 | Operational | 2024-12-16 | 56 | 11/6/2020, 9/23/2023, 8/7/2024 | 2025-02-05 | 57 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation; construction delays; customer enrollment | Yes; unspecified | 12/11/2024 - Certification | None | 1 | 1 | 1
SPQ0070 | PGE | PGE-2020-51 | Dunn Rd | Operational | Neighborhood Power | Neighborhood Power | 1 | No | 1848 | 2020-05-07 | 2021-12-22 | Operational | 2021-02-11 | Operational | 2021-03-01 | 9 | 2/17/2020, 9/11/2020 | 2021-02-11 | 9 | No | No | No | No | NA | None
SPQ0164 | PGE | PGE-2020-41 | Fruitland Creek Solar | Operational | TLS Capital | HEP | 1 | No | 1750 | 2020-04-27 | 12/12/2021, 12/12/2022 | Operational | 2022-11-30 | Operational | 2022-12-15 | 31 | 9/27/2019, 9/11/2020 | 2024-05-14 | 49 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation | No | NA | None | 1 | 1
OCS012 | PAC | PP-2020-63 | Goodling Annex | Certified | Bonneville Environmental Foundation | Bonneville Environmental Foundation | 1 | Yes | 1000 | 2020-04-27 | 10/21/2021, 4/1/2023, 2/28/2024 | Certified | 2024-10-30 | 57.9276 | Not Yet Operational | 54 | 2022-05-30 | 2024-09-13 | 53 | No | No | Yes; waiting for grant funding | No | 10/30/2024 - Certification | None | 1 | 1
OCS045 | PAC | PP-2021-99 | Green Solar | Operational | Greenkey Solar | SolRiver Capital | 2 | No | 2875 | 2022-04-15 | 2023-10-15 | Operational | 2024-06-25 | Operational | 2024-07-01 | 26 | Not Applicable | 2022-10-21 | 6 | No | Yes | No | Yes; IX construction delays | 6/25/2024 - Certification | None | 1 |  | 1
SPQ0157 | PGE | PGE-2020-37 | Gun Club Solar LLC | Operational | Conifer Energy Partners | Luminace | 2 | No | 2500 | 2022-04-15 | 10/15/2023, 10/31/2024 | Operational | 2024-12-11 | Operational | 2024-12-16 | 32 | 12/1/2019, 11/15/2023 | 2024-10-31 | 31 | No | Yes | Yes; contractor schedule constraints; inability to construct during winter | No | 12/11/2024 - Certification | None | 1 | 1
OCS018 | PAC | PP-2021-110 | Hay Creek Solar | Operational | TLS Capital | TLS Capital | 2 | No | 567 | 2022-04-15 | 2023-10-15 | Operational | 2022-12-14 | Operational | 2023-08-01 | 8 | 10/9/2021, 8/15/2022 | 2022-11-14 | 7 | No | No | No | No | NA | None
CSQ0002 | PGE | PGE-2020-70 | Jim and Salle's Place Apartments | Operational | Rose CDC | Rose CDC | 1 | Yes | 40 | 2020-04-27 | 10/21/2021, 4/21/2022 | Operational | 2022-05-18 | Operational | 2022-06-03 | 25 | 2020-09-30 | 2022-08-15 | 28 | No | No | Yes; PPA delay | No | NA | None | 1 | 1
SPQ0094 | PGE | PGE-2020-42 | Kaiser Creek Solar LLC | Operational | HEP | HEP | 1 | No | 2000 | 2020-04-27 | 12/18/2021, 6/12/2022, 12/18/2022 | Operational | 2022-11-30 | Operational | 2022-12-15 | 31 | 6/19/2020, 1/27/2021 | 2022-12-13 | 32 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation | No | NA | None | 1 | 1
OCS039 | PAC | PP-2021-97 | Kelly Creek Solar | Pre-Certified | Coast Energy, LLC | Coast Energy, LLC | 2 | No | 2250 | 2022-04-15 | 10/15/2023, 10/30/2024 | 2024-12-06 | Not Yet Certified | 34.3092 | Not Yet Operational | Not Yet Certified | 11/18/2022, 9/30/2023 | 2024-12-06 | 32 | Yes | No | Yes; contractor schedule constraints; inability to construct during winter | No | 11/12/2023 - Cert Extension Request | None | 1 | 1
SPQ0272 | PGE | PGE-2023-167 | Lincoln Solar LLC | Pre-Certified | Conifer Energy Partners | Conifer Energy Partners | 2 | No | 2985 | 2023-12-23 | NA | 2025-06-23 | Not Yet Certified | 14.0132 | Not Yet Operational | Not Yet Certified | Not Applicable | Project is still under the study process | Not Applicable | No | No | No | No | 12/22/2023 - Pre-Certification | None
OCS025 | PAC | PP-2020-80 | Linkville Solar | Operational | TLS Capital | HEP | 1 | No | 2800 | 2020-11-17 | 5/17/2022, 11/17/2022, 5/17/2023, 11/17/2023 | Operational | 2023-12-29 | Operational | 2024-05-03 | 37 | 10/29/2021 | 2023-08-31 | 33 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation; | Yes; fiber work delayed | 6/10/2023- Cert Extension Request | None | 1 | 1 | 1
OCS078 | PAC | PP-2024-179 | Lomaside Solar | Pre-Certified | Hawthorne Renewables LLC | Evergreen | 2 | Yes | 1100 | 2024-11-08 | NA | 2026-05-08 | Not Yet Certified | 3.4539 | Not Yet Operational | Not Yet Certified | 2025-09-30 | 2025-12-19 | 13 | No | Yes | No | No | 11/8/2024 - Pre-Certification | New COD
OCS027 | PAC | PP-2020-82 | Marble Solar | Certified | Sulus | SolRiver Capital | 1 | No | 2875 | 2020-12-29 | 12/29/2021, 6/29/2022, 9/30/2023, 7/30/2024 | 2025-03-15 | 2025-01-22 | 49.8355 | Not Yet Operational | 49 | 10/29/2021, 4/29/2022, | 2024-10-18 | 46 | No | Yes | Yes; US Dept of Commerce investigation; uncertainty of Tier 2 capacity release; wetland permitting delays; enrollment | Yes; awaiting updated IX agreement | 12/12/2024 - Cert Extension Request | Certified | 1 | 1 | 1
SPQ0093 | PGE | PGE-2020-53 | Marquam Creek Solar LLC | Operational | Greenkey Solar | Luminace | 2 | No | 1900 | 2022-04-15 | 10/14/2023, 10/14/2024 | Operational | 2024-12-11 | Operational | 2024-12-16 | 32 | 2/28/2020, 10/2/2023 | 2024-08-31 | 29 | No | Yes | Yes; contractor schedule constraints; inability to construct during winter | No | 12/11/2024 - Certification | None | 1 | 1
OCS064 | PAC | PP-2021-122 | McKinley Solar LLC | CANCELED | Sulus | Hawthorne Renewables LLC | 2 | No | 450 | 2022-08-23 | 2/23/2024, 12/31/2024, 8/30/2025 | Cancelled | Not Yet Certified | 30.0329 | Not Yet Operational | Not Applicable | 12/9/2022, 12/8/2023 | 2025-04-30 | 32 | Not Applicable | No | Yes; contractor schedule constraints; project financing delays | No | 11/9/2024 - Cert Extension Request | CANCELED | 1 | 1
CSQ0004 | PGE | PGE-2021-115 | Mompano Solar | Pre-Certified | Greenkey Solar | Coast Energy, LLC | 2 | No | 2000 | 2022-04-15 | 10/15/2023, 10/30/2024 | 2024-12-30 | Not Yet Certified | 34.3092 | Not Yet Operational | Not Yet Certified | 12/9/2022, 9/13/2024 | 2024-12-09 | 32 | No | Yes | Yes; contractor schedule constraints; inability to construct during winter; enrollment | No | 12/4/2024 - Certification Extension | None | 1 | 1
SPQ0124 | PGE | PGE-2020-52 | Mt Hope Solar | Operational | Neighborhood Power | Neighborhood Power | 1 | No | 2502 | 2020-05-07 | 2021-12-22 | Operational | 2021-02-11 | Operational | 2021-03-01 | 9 | 5/8/2020, 9/11/2020 | 2022-12-13 | 31 | No | No | No | No | NA | None
OCS035 | PAC | PP-2021-111 | Orchard Knob Solar | Operational | TLS Capital | Luminace | 2 | No | 2250 | 2022-04-15 | 10/15/2023, 1/15/2024, 9/11/2024, 11/11/2024 | Operational | 2024-10-30 | Operational | 2025-01-24 | 31 | 8/19/2022, 11/21/2022, 3/24/2023, 2/23/2024 | 2024-09-13 | 29 | No | Yes | Yes; time to provide relevant certification documents | Yes; IX work incomplete - material not ordered, waiting for revised IX timeline, confirm outstanding easements | 10/30/2024 - Certification | Operational | 1 | 1 | 1
OCS042 | PAC | PP-2020-78 | Oregon Shakespeare Festival Community Solar Project | Operational | Oregon Clean Power Cooperative | Oregon Clean Power Cooperative | 1 | Yes | 129.6 | 2020-11-05 | 2022-05-03 | Operational | 2021-09-22 | Operational | 2022-03-14 | 11 | Not Applicable | 2021-07-30 | 9 | No | No | No | No | NA | None
OCS057 | PAC | PP-2020-88 | Perrydale Solar | Pre-Certified | Sulus; SolRiver Capital | Evergreen | 2 | No | 999.99 | 2022-04-15 | 10/15/2023, 12/31/2023, 8/5/2024 | 2024-12-18 | Not Yet Certified | 34.3092 | Not Yet Operational | Not Yet Certified | 3/3/2023, 7/21/2023, 8/9/2024, 10/4/2024 | 2025-05-09 | 37 | No | Yes | No | Yes; equipment lead times and crew availability | 10/23/2024 - Cert Extension Request | New COD | 1 |  | 1
Q0666 | PAC | PP-2020-13 | Pilot Rock Solar 1 | Pre-Certified | Sunthurst | Sunthurst | 1 | No | 1980 | 2020-03-13 | 10/11/2021, 3/15/2024 | 2025-09-30 | Not Yet Certified | 59.4079 | Not Yet Operational | Not Yet Certified | 5/15/2017, 9/15/2017, 9/30/2018, 6/30/2019, 12/31/2019, 12/31/2022, 5/25/2023 | 2025-09-30 | 67 | No | No | Yes; COVID-19, lingering impacts of the US commerce investigation | Yes; delays in securing a utility PPA and IX agreement | 8/17/2023 - Cert Extension Request | None | 1 | 1 | 1
Q1045 | PAC | PP-2020-71 | Pilot Rock Solar 2 | Pre-Certified | Sunthurst | Sunthurst | 1 | No | 2990 | 2020-04-27 | 10/21/2021, 3/15/2023 | 2025-09-30 | Not Yet Certified | 57.9276 | Not Yet Operational | Not Yet Certified | 12/31/2022, 5/25/2023 | 2025-09-30 | 65 | No | No | Yes; COVID-19, lingering impacts of the US commerce investigation | Yes; delays in securing a utility PPA and interconnection agreement | 8/17/2023 - Cert Extension Request | None | 1 | 1 | 1
OCS036 | PAC | PP-2020-84 | Pine Grove Solar | Operational | TLS Capital | Luminace | 1 | No | 1400 | 2020-12-29 | 6/29/2022, 12/29/2022, 8/25/2023 | Operational | 2023-10-18 | Operational | 2025-01-21 | 34 | 8/5/2022, 11/14/2022, 8/21/2023, 2/16/2024 | 2024-07-03 | 42 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation; | Yes; delayed utility timeline | 7/6/2024 - Operation Extension | None | 1 | 1 | 1
SPQ0058 | PGE | PGE-2020-40 | Red Prairie Solar | Operational | TLS Capital | TLS Capital | 1 | No | 2200 | 2020-03-13 | 2021-09-11 | Operational | 2021-10-06 | Operational | 2021-10-19 | 19 | 11/16/2019, 2/26/2021 | 2022-12-13 | 33 | No | No | No | No | NA | None
OCS061 | PAC | PP-2024-184 | Reservoir Solar LLC | Pre-Certified | Hawthorne Renewables LLC | Hawthorne Renewables LLC | 2 | Yes | 875 | 2024-11-23 | NA | 2026-05-23 | Not Yet Certified | 2.9605 | Not Yet Operational | Not Yet Certified | Not Applicable | 2025-03-28 | Not Applicable | Yes | No | No | No | 11/23/2024 - Pre-certification | None
SPQ0125 | PGE | PGE-2020-1 | River Valley | Operational | Neighborhood Power | Neighborhood Power | 2 | No | 1998 | 2022-04-21 | 2023-10-21 | Operational | 2022-12-14 | Operational | 2023-02-01 | 8 | 2020-05-26 | 2022-12-13 | 8 | No | No | No | No | NA | None
SPQ0261 | PGE | PGE-2023-161 | Rodeo Solar | Pre-Certified | Conifer Energy Partners | Kendall Sustainable Infrastructure | 2 | No | 2250 | 2023-09-21 | 2025-03-25 | 2025-12-12 | Not Yet Certified | 17.0724 | Not Yet Operational | Not Yet Certified | Not Applicable | 2025-12-12 | 27 | No | Yes | No | No | 7/24/2024 - Cert Extension Request | None
CSQ0013 | PGE | PGE-2024-171 | Rosa Community Solar | Pre-Certified | Oregon Clean Power Cooperative | Oregon Clean Power Cooperative | 2 | Yes | 720 | 2024-09-24 | NA | 2026-03-24 | Not Yet Certified | 4.9342 | Not Yet Operational | Not Yet Certified | Not Applicable | 2025-04-01 | 6 | Yes | No | No | No | 9/24/2024 - Pre-Certification | Applicant negotiating a revised COD
OCS034 | PAC | PP-2020-86 | Round Lake Solar | Operational | TLS Capital | Luminace | 1 | No | 978 | 2020-12-29 | 6/29/2022, 12/29/2022, 8/25/2023 | Operational | 2023-10-18 | Operational | 2024-12-19 | 34 | 12/30/2021, 6/15/2022, 8/15/2022, 8/11/2023, 3/29/2024 | 2024-08-28 | 44 | Yes | Yes | Yes; COVID-19, US Dept of Commerce investigation; | Yes; delayed utility timeline | 7/6/2024 - Operation Extension | None | 1 | 1 | 1
SPQ0071 | PGE | PGE-2020-38 | Sandy River Solar | Operational | TLS Capital | HEP | 1 | No | 1850 | 2020-04-27 | 12/20/2021, 6/12/2022, 12/12/2022 | Operational | 2022-11-30 | Operational | 2022-12-15 | 31 | 3/2/2020, 12/1/2020 | 2023-02-27 | 34 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation | No | NA | None | 1 | 1
SPQ0181 | PGE | PGE-2020-45 | Sesqui-C Solar LLC | Operational | Conifer Energy Partners | HEP | 1 | No | 2500 | 2020-04-27 | 12/12/2021, 6/12/2022, 12/12/2022 | Operational | 2022-11-30 | Operational | 2022-12-15 | 31 | 3/12/2021, 5/21/2021 | 2022-12-13 | 32 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation; participant enrollment | No | NA | None | 1 | 1
CSQ0001 | PGE | PGE-2020-10 | Sheridan Solar | Operational | Pacific Northwest Solar LLC | SolRiver Capital | 2 | No | 3000 | 2022-05-25 | 2023-11-25 | Operational | 2024-06-25 | Operational | 2024-07-01 | 25 | Not Applicable | 2023-12-30 | 19 | No | Yes | No | No | 6/25/2024 - Certification | None
SPQ0067 | PGE | PGE-2020-22 | Skyward Solar | Operational | Nautilus Solar | Standard Solar | 1 | No | 2500 | 2020-03-13 | 9/1/2021, 7/1/2022, 1/1/2023 | Operational | 2022-11-30 | Operational | 2022-12-01 | 33 | 1/8/2020, 11/22/2022 | 2022-12-13 | 33 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation | No | NA | None | 1 | 1
CSQ0010 | PGE | PGE-2022-148 | Solar Harvest | Operational | Oregon Clean Power Cooperative | Oregon Clean Power Cooperative | 2 | Yes | 300 | 2022-10-08 | NA | Operational | 2024-05-17 | Operational | 2024-05-21 | 19 | 2021-10-29 | 2024-09-06 | 23 | No | No | No | No | 5/17/2024 - Certification | None
OCS047 | PAC | PP-2021-93 | Sunset Ridge Solar | Certified | Greenkey Solar | Luminace | 1 | No | 2250 | 2021-04-20 | 10/22/2022, 4/20/2023, 6/20/2023, 10/20/2023, 12/14/2023, 6/11/2024, 8/11/2024; 8/22/2024 | Certified | 2024-10-30 | 46.1513 | Not Yet Operational | 42 | 12/15/2022, 9/22/2023 | 2024-08-23 | 40 | No | Yes | Yes; COVID-19, US Dept of Commerce investigation; construction delays; | Yes; awaiting PPA; fiber optic material not ordered; IX design incomplete; incomplete IX work; finalizing inspections | 10/30/2024 - Certification | None | 1 | 1 | 1
OCS024 | PAC | PP-2020-81 | Tutuilla Solar | Pre-Certified | Sunthurst | Sunthurst | 1 | No | 1560 | 2020-11-17 | 5/17/2022, 5/17/2023, 11/17/2024 | 2024-11-17 | Not Yet Certified | 51.2171 | Not Yet Operational | Not Yet Certified | 12/30/2022, 5/25/2023 | 2025-09-30 | 58 | No | No | Yes; land lease delays | No | 6/23/2022- Cert Extension Request | None | 1 | 1
532 | IP | IP-2020-72 | Verde Light Community Solar | Operational | Fleet Development | Fleet Development | 1 | No | 2950 | 2020-06-18 | 6/16/2023, 3/16/2024 | Operational | 2024-06-12 | Operational | 2024-06-13 | 48 | Not Applicable | 2021-10-29 | 16 | No | No | Yes; Dept of Commerce investigation, waiting for grant funding; completing enrollment | No | 6/12/2024 - Certification | None | 1 | 1
SPQ0240 | PGE | PGE-2020-77 | Wallace Solar LLC | Certified | Sulus | SolRiver Capital | 2 | No | 2970 | 2022-04-15 | 10/15/2023, 7/30/2024 | 2025-03-15 | 2025-01-22 | 34.3092 | Not Yet Operational | 33 | 5/31/2023, 7/1/2024 | 2024-12-20 | 32 | No | Yes | Yes; supply chain delays; permitting delays | Yes; unspecified | 12/12/2024 - Cert Extension Request | Certified | 1 | 1
OCS005 | PAC | PP-2020-35 | Wallowa County Community Solar | Operational | Fleet Development | Fleet Development | 1 | Yes | 360 | 2020-04-27 | 2021-09-25 | Operational | 2022-02-09 | Operational | 2022-07-01 | 21 | 6/4/2021 | 2021-12-30 | 20 | No | No | No | No | NA | None
SPQ0179 | PGE | PGE-2020-18 | Waterford Solar | Pre-Certified | Solar Town | Luminace | 2 | No | 2565 | 2022-04-30 | 11/2/2023, 8/31/2024 | 2025-07-01 | Not Yet Certified | 33.8158 | Not Yet Operational | Not Yet Certified | 7/17/2020, 5/31/2022 | 2024-07-26 | 27 | No | Yes | Yes; construction delays | Yes; unspecified | 2/8/2025- Cert Extension Request | New Certification deadline | 1 | 1 | 1
OCS020 | PAC | PP-2021-92 | Whisky Creek Solar | Operational | TLS Capital | TLS Capital | 1 | Yes | 165 | 2021-04-20 | 10/20/2022, 6/12/2022, 12/12/2022 | Operational | 2022-12-14 | Operational | 2023-07-06 | 20 | Not Applicable | 2022-08-15 | 16 | No | No | Yes; COVID-19, US Dept of Commerce investigation | No | NA | None | 1 | 1
SPQ0166 | PGE | PGE-2020-48 | Williams Acres | Operational | Neighborhood Power | Neighborhood Power | 1 | No | 2502 | 2020-05-07 | 2021-12-12 | Operational | 2021-02-11 | Operational | 2021-04-05 | 9 | 7/6/2020, 8/13/2020 | 2021-02-11 | 9 | No | No | No | No | NA | None
OCS019 | PAC | PP-2020-85 | Wocus Marsh Solar | Operational | TLS Capital | TLS Capital | 1 | No | 882 | 2021-04-20 | 10/20/2022, 4/20/2023 | Operational | 2022-12-14 | Operational | 2023-08-01 | 20 | 11/5/2021 | 2022-08-15 | 16 | No | No | Yes; US commerce investigation | No | NA | None | 1 | 1
OCS074 | PAC | PP-2021-126 | Wood River Solar | Operational | TLS Capital | TLS Capital | 1 | Yes | 359 | 2021-12-28 | 6/28/2023, 12/31/2023, 8/5/2024 | Operational | 2024-07-10 | Operational | 2025-01-08 | 30 | 2023-11-15 | 2024-06-28 | 30 | No | No | Yes; equipment procurement, contractor schedule constraints | Yes; unspecified | 7/10/2024- Certification | None | 1 | 1 | 1
SPQ0163 | PGE | PGE-2020-55 | Zena Solar LLC | Operational | Conifer Energy Partners | UGEI | 2 | No | 2500 | 2022-04-15 | 10/15/2023, 7/26/2024 | Operational | 2024-12-11 | Operational | 2024-12-20 | 32 | 3/4/2022, 2/2/2024 | 2024-12-31 | 33 | No | Yes | Yes; construction delays | Yes; unspecified | 12/11/2024 - Certification | None | 1 | 1 | 1

## Operational Projects (hidden)
Interconnection Queue Number | Utility Service Area | Project ID | Project Name | CSP Project Status | Original owner entity | Current owner entity | Pre-certification Date | Prior Certification Deadlines | Date Certified | Months to Certification | Prior CODs | Current Commercial Operation Date | Months to Current Commercial Operation Date | History of PM transfers? | History of Project Development Delays? | History of IX Delays? | Review notes
SPQ0158 | PGE | PGE-2020-56 | Carnes Creek Solar LLC | Operational | Conifer Energy Partners | Conifer Energy Partners | 2020-06-12 | 12/12/21; 6/12/22 | #REF! | #REF! |  | 2022-12-15 | 0 | No | Yes; COVID-19, US Dept of Commerce investigation | NA
OCS044 | PAC | PP-2021-116 | Cherry Creek Solar | Operational | TLS Capital | GreenKey Solar | 2021-07-27 | 2023-01-27 | #REF! | #REF! |  |  |  | Yes | Yes; COVID-19, US Dept of Commerce investigation | NA
SPQ0152 | PGE | PGE-2020-34 | Cosper Creek Solar LLC | Operational | TLS Capital | HEP | 2020-06-12 | 12/12/2021;6/12/2022; 12/12/2022 | #REF! | #REF! |  |  |  | Yes | Yes; COVID-19, US Dept of Commerce investigation | NA
SPQ0070 | PGE | PGE-2020-51 | Dunn Rd | Operational | Neighborhood Power | Neighborhood Power | 2020-06-22 | 2021-12-22 | #REF! | #REF! |  |  |  | No | NA | NA
SPQ0164 | PGE | PGE-2020-41 | Fruitland Creek Solar | Operational | TLS Capital | HEP | 2020-06-12 | 12/12/2021; 12/12/2022 | #REF! | #REF! |  |  |  | Yes | Yes; COVID-19, US Dept of Commerce investigation | NA
OCS018 | PAC | PP-2021-110 | Hay Creek Solar | Operational | TLS Capital | TLS Capital | 2022-04-15 | 2023-10-15 | #REF! | #REF! |  |  |  | No | NA | NA
PGE QF - 00266 | PGE | PGE-2020-70 | Jim and Salle's Place Apartments | Operational | Rose CDC | Rose CDC | 2020-04-21 | 10/21/2021; 4/21/2022 | #REF! | #REF! |  |  |  | No | Yes; PPA delay | NA
SPQ0094 | PGE | PGE-2020-42 | Kaiser Creek Solar LLC | Operational | HEP | GreenKey Solar | 2020-06-18 | 12/18/2021;6/12/2022; 12/18/2022 | #REF! | #REF! |  |  |  | Yes | Yes; COVID-19, US Dept of Commerce investigation | NA
SPQ0124 | PGE | PGE-2020-52 | Mt Hope Solar | Operational | Neighborhood Power | Neighborhood Power | 2020-06-22 | 2021-12-22 | #REF! | #REF! |  |  |  | No | NA | NA
OCS042 | PAC | PP-2020-78 | Oregon Shakespeare Festival Community Solar Project | Operational | Oregon Clean Power Cooperative | Oregon Clean Power Cooperative | 2020-11-03 | 2022-05-03 | #REF! | #REF! |  |  |  | No | NA | NA
SPQ0058 | PGE | PGE-2020-40 | Red Prairie Solar | Operational | TLS Capital | TLS Capital | 2020-03-11 | 2021-09-11 | #REF! | #REF! |  |  |  | No | NA | NA
SPQ0125 | PGE | PGE-2020-1 | River Valley | Operational | Neighborhood Power | Neighborhood Power | 2022-04-21 | 2023-10-21 | #REF! | #REF! |  |  |  | No | NA | NA
SPQ0071 | PGE | PGE-2020-38 | Sandy River Solar | Operational | TLS Capital | HEP | 2020-06-12 | 12/20/2021; 6/12/2022;12/12/2022 | #REF! | #REF! |  |  |  | Yes | Yes; COVID-19, US Dept of Commerce investigation | NA
SPQ0181 | PGE | PGE-2020-45 | Sesqui-C Solar LLC | Operational | Conifer Energy Partners | HEP | 2020-06-12 | 12/12/2021;6/12/2022;12/12/2022 | #REF! | #REF! |  |  |  | Yes | Yes; COVID-19, US Dept of Commerce investigation; participant enrollment | NA
SPQ0067 | PGE | PGE-2020-22 | Skyward Solar | Operational | Nautilus Solar | Standard Solar | 2020-03-11 | 9/1/2021;7/1/2022; 1/1/2023 | #REF! | #REF! |  |  |  | Yes | Yes; COVID-19, US Dept of Commerce investigation
OCS005 | PAC | PP-2020-35 | Wallowa County Community Solar | Operational | Fleet Development | Fleet Development | 2020-03-25 | 2021-09-25 | #REF! | #REF! |  |  |  | No | NA | NA
OCS020 | PAC | PP-2021-92 | Whisky Creek Solar | Operational | TLS Capital | TLS Capital | 2021-04-20 | 10/20/2022;6/12/2022;12/12/2022 | #REF! | #REF! |  |  |  | No | Yes; COVID-19, US Dept of Commerce investigation | NA
SPQ0166 | PGE | PGE-2020-48 | Williams Acres | Operational | Neighborhood Power | Neighborhood Power | 2020-06-22 | 2021-12-12 | #REF! | #REF! |  |  |  | No | NA | NA
OCS019 | PAC | PP-2020-85 | Wocus Marsh Solar | Operational | TLS Capital | TLS Capital | 2021-04-20 | 10/20/2022;4/20/2023 | #REF! | #REF! |  |  |  | No | Yes; US commerce investigation | NA

## OPUC Project Decisions
History of OPUC Decisions on CSP Project Recommendations
Highlighted cells indicate update since previous report
Interconnection Queue Number | Utility Service Area | CSP Project ID | CSP Project Name | Project Manager | Recommendation Type | Effective Date | Link to PA Recommendation or Commission Decision in Docket No. UM 1930
SPQ0179 | PGE | PGE-2020-18 | Waterford Solar | Solar Town LLC | Certification Extension | 2025-02-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah334443054.pdf
SPQ0240 | PAC | PGE-2020-77 | Wallace Solar LLC | Wallace Solar LLC | Certification Recommendation | 2025-01-22 | https://apps.puc.state.or.us/orders/2025ords/25-014.pdf
OCS027 | PAC | PP-2020-82 | Marble Solar | Marble Solar LLC | Certification Recommendation | 2025-01-22 | https://apps.puc.state.or.us/orders/2025ords/25-014.pdf
OCS034 | PAC | PP-2020-84 | Pine Grove Solar | Pine Grove PM LLC | Operational Date Extension | 2024-12-31 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah333527053.pdf
OCS034 | PAC | PP-2020-86 | Round Lake Solar | Round Lake PM, LLC | Operational Date Extension | 2024-12-31 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah333527053.pdf
SPQ0240 | PGE | PGE-2020-77 | Wallace Solar LLC | Wallace Solar LLC | Certification Extension | 2024-12-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah333274032.pdf
OCS027 | PAC | PP-2020-82 | Marble Solar | Marble Solar LLC | Certification Extension | 2024-12-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah333274032.pdf
SPQ0163 | PGE | PGE-2020-55 | Zena Solar, LLC | Zena Solar, LLC | Certification Recommendation with a waiver | 2024-12-11 | https://apps.puc.state.or.us/orders/2024ords/24-437.pdf
532 | IP | IP-2020-72 | Verde Light Community Solar | Fleet Development | Waiver Request | 2024-12-11 | https://apps.puc.state.or.us/orders/2024ords/24-438.pdf
SPQ0093 | PGE | PGE-2020-53 | Marquam Creek Solar LLC | Marquam Creek Project Manager LLC | Certification Recommendation | 2024-12-11 | https://apps.puc.state.or.us/orders/2024ords/24-437.pdf
SPQ0157 | PGE | PGE-2020-37 | Gun Club Solar LLC | Conifer Community Energy 2 LLC | Certification Recommendation | 2024-12-11 | https://apps.puc.state.or.us/orders/2024ords/24-437.pdf
SPQ0193 | PGE | PGE-2020-19 | Dover Solar | Solar Town LLC | Certification Recommendation with a waiver | 2024-12-11 | https://apps.puc.state.or.us/orders/2024ords/24-437.pdf
SPQ0220 | PGE | PGE-2020-11 | Cork Solar LLC | Solar Town LLC | Certification Recommendation | 2024-12-11 | https://apps.puc.state.or.us/orders/2024ords/24-437.pdf
OCS049 | PAC | PP-2021-113 | Chapman Creek Solar | Chapman Creek PM LLC | Certification Recommendation with a waiver | 2024-12-11 | https://apps.puc.state.or.us/orders/2024ords/24-437.pdf
SPQ0191 | PGE | PGE-2020-21 | Buckner Creek Solar LLC | Conifer Community Energy LLC | Certification Recommendation with a waiver | 2024-12-11 | https://apps.puc.state.or.us/orders/2024ords/24-437.pdf
SPQ0186 | PGE | PGE-2020-15 | Belvedere Solar | Belvedere Solar PM, LLC | Certification Recommendation | 2024-12-11 | https://apps.puc.state.or.us/orders/2024ords/24-437.pdf
SPQ0163 | PGE | PGE-2020-55 | Zena Solar, LLC | Zena Solar, LLC | Certification Extension | 2024-12-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah333061025.pdf
CSQ0004 | PGE | PGE-2021-115 | Mompano Solar | Mompano Solar Project Manager LLC | Certification Extension | 2024-12-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah333061025.pdf
SPQ0093 | PGE | PGE-2020-53 | Marquam Creek Solar LLC | Marquam Creek Project Manager LLC | Certification Extension | 2024-12-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah333061025.pdf
SPQ0157 | PGE | PGE-2020-37 | Gun Club Solar LLC | Conifer Community Energy 2 LLC | Certification Extension | 2024-12-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah333061025.pdf
SPQ0193 | PGE | PGE-2020-19 | Dover Solar | Solar Town LLC | Certification Extension | 2024-12-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah333061025.pdf
SPQ0220 | PGE | PGE-2020-11 | Cork Solar LLC | Solar Town LLC | Certification Extension | 2024-12-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah333061025.pdf
OCS049 | PAC | PP-2021-113 | Chapman Creek Solar | Chapman Creek PM LLC | Certification Extension | 2024-12-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah333061025.pdf
SPQ0186 | PGE | PGE-2020-15 | Belvedere Solar | Belvedere Solar PM, LLC | Certification Extension | 2024-12-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah333061025.pdf
OCS061 | PAC | PP-2020-89 | Reservoir Solar | Hawthorne Renewables | Pre-certification Recommendation | 2024-11-23 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah332893025.pdf
OCS067 | PAC | PP-2022-138 | Colfax Solar LLC | Hawthorne Renewables | Pre-certification Recommendation | 2024-11-23 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah332893025.pdf
OCS064 | PAC | PP-2021-122 | McKinley Solar LLC | Hawthorne Renewables LLC | Certification Extension | 2024-11-09 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah332422025.pdf
OCS058 | PAC | PP-2021-121 | Coker Solar | Hawthorne Renewables LLC | Certification Extension | 2024-11-09 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah332422025.pdf
OCS051 | PAC | PP-2021-142 | Canyonville Solar 2 | Canyonville Solar 2 LLC | Certification Extension | 2024-11-09 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah332421033.pdf
OCS050 | PAC | PP-2021-94 | Canyonville Solar 1 | Canyonville Solar 1 LLC | Certification Extension | 2024-11-09 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah332421033.pdf
OCS078 | PAC | PP-2024-179 | Lomaside Solar | Hawthorne Renewables LLC | Pre-Certification Recommendation | 2024-11-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah332374033.pdf
OCS071 | PAC | PP-2024-185 | Almon Solar | Hawthorne Renewables LLC | Pre-Certification Recommendation | 2024-11-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah332374033.pdf
OCS047 | PAC | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge Project Manager, LLC | Certification Recommendation | 2024-10-30 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau332364025.pdf
OCS035 | PAC | PP-2021-11 | Orchard Knob Solar | Orchard Knob PM, LLC | Certification Recommendation | 2024-10-30 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau332364025.pdf
OCS012 | PAC | PP-2020-63 | Goodling Annex | Bonneville Environmental Foundation | Certification Recommendation | 2024-10-30 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau332364025.pdf
SPQ0180 | PGE | PGE-2020-17 | Clayfield Solar LLC | Clayfield Solar PM, LLC | Certification Recommendation | 2024-10-30 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau332364025.pdf
SPQ0262 | PGE | PGE-2024-183 | Crawford Solar | Hawthorne Renewables LLC | Pre-certification recommendation | 2024-10-24 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah331973025.pdf
SPQ0266 | PGE | PGE-2023-157 | Apricus Solar, LLC | Conifer Community Energy 7, LLC | Certification Extension | 2024-10-24 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah331974025.pdf
OCS047 | PAC | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge Project Manager, LLC | Certification Extension | 2024-10-23 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah331912120.pdf
OCS057 | PAC | PP-2020-88 | Perrydale Solar LLC | Perrydale Solar LLC | Certification Extension | 2024-10-23 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah331908120.pdf
OCS035 | PAC | PP-2021-111 | Orchard Knob Solar | Orchard Knob PM, LLC | Certification Extension | 2024-10-23 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah331912120.pdf
CSQ0013 | PGE | PGE-2024-171 | Rosa Community Solar | Oregon Clean Power Cooperative | Pre-certification Recommendation | 2024-09-24 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah331226025.pdf
C3-178 | PAC | PP-2024-176 | Chaberton Solar Horton Rim LLC | Chaberton Solar Horton Rim LLC | Pre-certification Recommendation | 2024-09-24 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah331226025.pdf
C3-014 | PAC | PP-2024-175 | Chaberton Solar Diamond Peak LLC | Chaberton Solar Diamond Peak LLC | Pre-certification Recommendation | 2024-09-24 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah331226025.pdf
SPQ0180 | PGE | PGE-2020-17 | Clayfield Solar LLC | Clayfield Solar PM, LLC | Certification Extension | 2024-09-20 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah331168120.pdf
OCS047 | PAC | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge Project Manager, LLC | Certification Extension | 2024-07-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah329983054.pdf
SPQ0261 | PGE | PGE-2023-161 | Rodeo Solar | Conifer Community Energy 8 LLC | Certification Extension | 2024-07-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah329983054.pdf
OCS038 | PAC | PP-2021-112 | 7 Mile Solar | 7 Mile PM LLC | Certification Extension | 2024-07-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah329983054.pdf
OCS074 | PAC | PP-2021-126 | Wood River Solar | Wood River PM, LLC | Certification Recommendation | 2024-07-10 | https://apps.puc.state.or.us/orders/2024ords/24-226.pdf
OCS034 | PAC | PP-2020-86 | Round Lake Solar | Round Lake PM LLC | Operational Date Extension | 2024-07-10 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah329555024.pdf
OCS034 | PAC | PP-2020-84 | Pine Grove Solar | Pine Grove PM LLC | Operational Date Extension | 2024-07-10 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah329555024.pdf
OCS055 | PAC | PP-2021-125 | Blackwell Creek Solar | Blackwell Creek PM LLC | Certification Recommendation | 2024-07-10 | https://apps.puc.state.or.us/orders/2024ords/24-226.pdf
CSQ0001 | PGE | PGE-2020-10 | Sheridan Solar | Sheridan Solar LLC | Certification Recommendation | 2024-06-25 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau329489024.pdf
OCS045 | PAC | PP-2021-99 | Green Solar | Green Solar LLC | Certification Recommendation | 2024-06-25 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau329489024.pdf
SPQ0250 | PGE | PGE-2020-75 | Auburn Solar | Auburn Solar LLC | Certification Recommendation | 2024-06-25 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau329489024.pdf
532 | IP | IP-2020-72 | Verde Light Community Solar | Fleet Development LLC | Certification Recommendation | 2024-06-12 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau329110055.pdf
OCS046 | PAC | PP-2021-109 | Antelope Creek Solar | Antelope Creek PM LLC | Certification Recommendation | 2024-06-12 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau329110055.pdf
CSQ0014 | PGE | PGE-2024-180 | CP Sheridan | CP Sheridan | Pre-certification Recommendation | 2024-05-31 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah328638113.pdf
SPQ0250 | PGE | PGE-2020-75 | Auburn Solar | Auburn Solar LLC | Certification Extension | 2024-05-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah328505024.pdf
CSQ0010 | PGE | PGE-2022-148 | Solar Harvest | Oregon Clean Power Cooperative | Certification Recommendation | 2024-05-17 | https://apps.puc.state.or.us/orders/2024ords/24-143.pdf
CSQ0015 | PGE | PGE-2024-177 | Bradley Solar 2 | Hawthorne Renewables LLC | Pre-certification Recommendation | 2024-05-17 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah328354033.pdf
532 | IP | IP-2020-72 | Verde Light Community Solar | Fleet Development LLC | Certification Extension | 2024-04-05 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah327471032.pdf
OCS012 | PAC | PP-2020-63 | Goodling Annex | Bonneville Environmental Foundation | Certification Extension | 2024-04-05 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah327471032.pdf
SPQ0193 | PGE | PGE-2020-19 | Dover Solar | Solar Town LLC | Certification Extension | 2024-04-05 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah327471032.pdf
OCS063 | PAC | PP-2021-103 | Buckaroo Solar 2 | Buckaroo Solar 2 LLC | Certification Extension | 2024-04-05 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah327471032.pdf
OCS062 | PAC | PP-2021-104 | Buckaroo Solar 1 LLC | Buckaroo Solar 1 LLC | Certification Extension | 2024-04-05 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah327471032.pdf
CSQ0001 | PGE | PGE-2020-10 | Sheridan Solar | Sheridan Solar LLC | Certification Extension | 2024-03-09 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326908023.pdf
OCS035 | PAC | PP-2021-111 | Orchard Knob Solar | Orchard Knob PM LLC | Certification Extension | 2024-03-09 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326884032.pdf
OCS046 | PAC | PP-2021-109 | Antelope Creek Solar | Antelope Creek PM LLC | Certification Extension | 2024-03-09 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326884032.pdf
OCS047 | PAC | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge Project Manager, LLC | Certification Extension | 2024-02-22 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326626023.pdf
OCS038 | PAC | PP-2021-112 | 7 Mile Solar | 7 Mile PM LLC | Certification Extension | 2024-02-22 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326626023.pdf
SPQ0163 | PGE | PGE-2020-55 | Zena Solar LLC | Zena Solar, LLC | PM Transfer | 2024-02-21 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326608023.pdf
OCS074 | PAC | PP-2021-126 | Wood River Solar | Wood River PM, LLC | Certification Extension | 2024-01-05 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah325686023.pdf
OCS057 | PAC | PP-2020-88 | Perrydale Solar | Perrydale Solar LLC | Certification Extension | 2024-01-05 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah325686023.pdf
OCS025 | PAC | PP-2020-80 | Linkville Solar | Linkville PM LLC | Certification Recommendation | 2023-12-29 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau325671054.pdf
SPQ0272 | PGE | PGE-2023-167 | Lincoln Solar LLC | CCE 9 LLC | Pre-certification Recommendation | 2023-12-23 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah325483023.pdf
OCS035 | PAC | PP-2021-111 | Orchard Knob Solar | Orchard Knob PM LLC | Certification Extension | 2023-11-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah16445.pdf
OCS046 | PAC | PP-2021-109 | Antelope Creek Solar | Antelope Creek PM LLC | Certification Extension | 2023-11-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah16445.pdf
SPQ0163 | PGE | PGE-2020-55 | Zena Solar LLC | Conifer Community Energy 6 LLC | Certification Extension | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
OCS047 | PAC | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge Project Manager LLC | Certification Extension | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
CSQ0004 | PGE | PGE-2021-115 | Mompano Solar | Mompano Solar Project Manager LLC | Certification Extension | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
OCS039 | PAC | PP-2021-97 | Kelly Creek Solar | Kelly Creek Project Manager LLC | Certification Extension | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
OCS045 | PAC | PP-2021-99 | Green Solar | Green Solar LLC | Certification Extension | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
OCS049 | PAC | PP-2021-113 | Chapman Creek Solar | Chapman Creek PM LLC | Certification Extension | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
SPQ0250 | PGE | PGE-2020-75 | Auburn Solar | Auburn Solar LLC | Certification Extension | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
OCS038 | PAC | PP-2021-112 | 7 Mile Solar | 7 Mile PM LLC | Certification Extension | 2023-11-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15210.pdf
OCS034 | PAC | PP-2020-86 | Round Lake Solar | Round Lake PM LLC | Certification Recommendation | 2023-10-18 | https://apps.puc.state.or.us/orders/2023ords/23-375.pdf
OCS036 | PAC | PP-2020-84 | Pine Grove Solar | Pine Grove PM LLC | Certification Recommendation | 2023-10-18 | https://apps.puc.state.or.us/orders/2023ords/23-375.pdf
OCS061 | PAC | PP-2020-89 | Reservoir Solar LLC | Sulus Solar | Certification Extension | 2023-10-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15137.pdf
OCS064 | PAC | PP-2021-122 | McKinley Solar LLC | Sulus Solar | Certification Extension | 2023-10-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15137.pdf
SPQ0191 | PGE | PGE-2020-21 | Buckner Creek Solar LLC | Conifer Community Energy LLC | Certification Extension | 2023-10-13 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15137.pdf
OCS061 | PAC | PP-2020-89 | Reservoir Solar LLC | Sulus Solar | PM Transfer | 2023-09-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah122749.pdf
OCS064 | PAC | PP-2021-122 | McKinley Solar LLC | Sulus Solar | PM Transfer | 2023-09-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah122749.pdf
OCS058 | PAC | PP-2021-121 | Coker Solar | Sulus Solar | PM Transfer | 2023-09-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah122749.pdf
OCS008 | PAC | PP-2020-76 | Burlingame Solar LLC | Burlingame Solar LLC | Certification Extension | 2023-09-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah94953.pdf
OCS040 | PAC | PP-2021-94 | Burg Solar | Sulus Solar | Certification Extension | 2023-09-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah94953.pdf
SPQ0261 | PGE | PGE-2023-161 | Rodeo Solar | Conifer Community Energy 8 LLC | Pre-certification Recommendation | 2023-09-21 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164944.pdf
SPQ0179 | PGE | PGE-2020-18 | Waterford Solar | Solar Town LLC | PM Transfer | 2023-08-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145421.pdf
SPQ0179 | PGE | PGE-2020-18 | Waterford Solar | Solar Town LLC | Certification Extension | 2023-08-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145613.pdf
SPQ0093 | PGE | PGE-2020-53 | Marquam Creek Solar LLC | Marquam Creek Project Manager LLC | Certification Extension | 2023-08-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145236.pdf
SPQ0157 | PGE | PGE-2020-37 | Gun Club Solar LLC | Conifer Community Energy 2 LLC | Certification Extension | 2023-08-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145236.pdf
SPQ0193 | PGE | PGE-2020-19 | Dover Solar | Solar Town LLC | Certification Extension | 2023-08-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145613.pdf
SPQ0220 | PGE | PGE-2020-11 | Cork Solar LLC | Solar Town LLC | Certification Extension | 2023-08-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145613.pdf
SPQ0220 | PGE | PGE-2020-11 | Cork Solar LLC | Solar Town LLC | PM Transfer | 2023-08-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145421.pdf
SPQ0180 | PGE | PGE-2020-17 | Clayfield Solar LLC | Clayfield Solar PM, LLC | Certification Extension | 2023-08-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145613.pdf
SPQ0180 | PGE | PGE-2020-17 | Clayfield Solar LLC | Solar Town LLC | PM Transfer | 2023-08-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145421.pdf
SPQ0186 | PGE | PGE-2020-15 | Belvedere Solar | Belvedere Solar PM, LLC | Certification Extension | 2023-08-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145613.pdf
SPQ0186 | PGE | PGE-2020-15 | Belvedere Solar | Solar Town LLC | PM Transfer | 2023-08-26 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah145421.pdf
OCS074 | PAC | PP-2021-126 | Wood River Solar | Wood River PM, LLC | Certification Extension | 2023-08-17 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah13247.pdf
532 | IP | IP-2020-72 | Verde Light Community Solar | Fleet Development LLC | Consent to Collateral Assignment | 2023-08-17 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah133250.pdf
Q1045 | PAC | PP-2020-71 | Pilot Rock Solar 2 | Pilot Rock Solar 2 LLC | Certification Extension w/ condition | 2023-08-17 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah133441.pdf
Q0666 | PAC | PP-2020-13 | Pilot Rock Solar 1 | Pilot Rock Solar 1 LLC | Certification Extension w/ condition | 2023-08-17 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah133441.pdf
SPQ0266 | PGE | PGE-2023-157 | Apricus Solar, LLC | Conifer Community Energy 7 LLC | Pre-certification Recommendation | 2023-07-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah155245.pdf
OCS019 | PAC | PP-2020-85 | Wocus Marsh Solar | Wocus Marsh PM LLC | Operational Date Extension | 2023-06-30 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah152727.pdf
OCS020 | PAC | PP-2021-92 | Whisky Creek Solar | Whisky Creek PM LLC | Operational Date Extension | 2023-06-30 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah152727.pdf
OCS018 | PAC | PP-2021-110 | Hay Creek Solar | Hay Creek PM LLC | Operational Date Extension | 2023-06-30 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah152727.pdf
OCS012 | PAC | PP-2020-63 | Goodling Annex | Bonneville Environmental Foundation | Certification Extension | 2023-06-30 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah152441.pdf
SPQ0071 | PGE | PGE-2020-38 | Sandy River Solar | Sandy River Solar LLC | Consent to Collateral Assignment | 2023-06-19 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah173011.pdf
SPQ0094 | PGE | PGE-2020-42 | Kaiser Creek Solar LLC | Kaiser Creek Project Manager LLC | Consent to Collateral Assignment | 2023-06-19 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah173011.pdf
SPQ0240 | PAC | PGE-2020-77 | Wallace Solar LLC | Wallace Solar LLC | Certification Extension | 2023-06-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah14537.pdf
532 | IP | IP-2020-72 | Verde Light Community Solar | Fleet Development LLC | Certification Extension | 2023-06-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah14537.pdf
OCS027 | PAC | PP-2020-82 | Marble Solar | Marble Solar LLC | Certification Extension | 2023-06-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah14537.pdf
OCS025 | PAC | PP-2020-80 | Linkville Solar | Linkville PM LLC | Certification Extension | 2023-06-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah14537.pdf
OCS051 | PAC | PP-2022-142 | Canyonville Solar 2 | Canyonville Solar 2 LLC | Certification Extension | 2023-06-10 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah14537.pdf
OCS050 | PAC | PP-2021-94 | Canyonville Solar 1 | Canyonville Solar 1 LLC | Certification Extension | 2023-06-10 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah14537.pdf
OCS047 | PAC | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge Project Manager LLC | Certification Extension | 2023-05-24 | https://edocs.puc.state.or.us/efdocs/HAC/um1930hac154159.pdf
OCS019 | PAC | PP-2020-85 | Wocus Marsh Solar | Wocus Marsh PM LLC | Consent to Collateral Assignment | 2023-04-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah111830.pdf
OCS020 | PAC | PP-2021-92 | Whisky Creek Solar | Whisky Creek PM LLC | Consent to Collateral Assignment | 2023-04-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah111830.pdf
OCS018 | PAC | PP-2021-110 | Hay Creek Solar | Hay Creek PM LLC | Consent to Collateral Assignment | 2023-04-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah111830.pdf
OCS044 | PAC | PP-2021-116 | Cherry Creek Solar | Cherry Creek Project Manager LLC | Consent to Collateral Assignment | 2023-04-12 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah111830.pdf
SPQ0181 | PGE | PGE-2020-45 | Sesqui-C Solar | Conifer Community Energy 3 LLC | Consent to Collateral Assignment | 2023-01-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah93220.pdf
SPQ0164 | PGE | PGE-2020-41 | Fruitland Creek Solar | FC PM LLC | Consent to Collateral Assignment | 2023-01-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah93220.pdf
SPQ0152 | PGE | PGE-2020-34 | Cosper Creek Solar LLC | Conifer Community Energy 1 LLC | Consent to Collateral Assignment | 2023-01-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah93220.pdf
SPQ0158 | PGE | PGE-2020-56 | Carnes Creek Solar | Conifer Community Energy 5 LLC | Consent to Collateral Assignment | 2023-01-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah93220.pdf
OCS019 | PAC | PP-2020-85 | Wocus Marsh Solar | Wocus Marsh PM LLC | Certification Recommendation | 2022-12-14 | https://apps.puc.state.or.us/orders/2022ords/22-481.pdf
OCS020 | PAC | PP-2021-92 | Whisky Creek Solar | Whisky Creek PM LLC | Certification Recommendation | 2022-12-14 | https://apps.puc.state.or.us/orders/2022ords/22-481.pdf
SPQ0125 | PGE | PGE-2020-1 | River Valley | Neighborhood Power | Certification Recommendation | 2022-12-14 | https://apps.puc.state.or.us/orders/2022ords/22-481.pdf
OCS018 | PAC | PP-2021-110 | Hay Creek Solar | Hay Creek PM LLC | Certification Recommendation | 2022-12-14 | https://apps.puc.state.or.us/orders/2022ords/22-481.pdf
OCS044 | PAC | PP-2021-116 | Cherry Creek Solar | Cherry Creek Project Manager LLC | Certification Recommendation | 2022-12-14 | https://apps.puc.state.or.us/orders/2022ords/22-481.pdf
OCS058 | PAC | PP-2021-121 | Coker Solar | Sulus Solar | Pre-certification Recommendation | 2022-12-01 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah152218.pdf
OCS055 | PAC | PP-2021-125 | Blackwell Creek Solar | Blackwell Creek PM LLC | Pre-certification Recommendation | 2022-12-01 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah152218.pdf
SPQ0067 | PGE | PGE-2020-22 | Skyward Solar | Skyward Solar LLC | Certification Recommendation | 2022-11-30 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau1616.pdf
SPQ0181 | PGE | PGE-2020-45 | Sesqui-C Solar | Sesqui-C Solar | Certification Recommendation | 2022-11-30 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau1616.pdf
SPQ0071 | PGE | PGE-2020-38 | Sandy River Solar | SR PM LLC | Certification Recommendation | 2022-11-30 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau1616.pdf
SPQ0094 | PGE | PGE-2020-42 | Kaiser Creek Solar LLC | Kaiser Creek Project Manager LLC | Certification Recommendation | 2022-11-30 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau1616.pdf
SPQ0164 | PGE | PGE-2020-41 | Fruitland Creek Solar | FC PM LLC | Certification Recommendation | 2022-11-30 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau1616.pdf
SPQ0152 | PGE | PGE-2020-34 | Cosper Creek Solar LLC | Conifer Community Energy 1 LLC | Certification Recommendation | 2022-11-30 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau1616.pdf
SPQ0158 | PGE | PGE-2020-56 | Carnes Creek Solar | Conifer Community Energy 5 LLC | Certification Recommendation | 2022-11-30 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau1616.pdf
SPQ0193 | PGE | PGE-2020-19 | Dover Solar | Solar Town LLC | Certification Extension | 2022-11-11 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah10130.pdf
SPQ0180 | PGE | PGE-2020-17 | Clayfield Solar LLC | Solar Town LLC | Certification Extension | 2022-11-11 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah10130.pdf
SPQ0186 | PGE | PGE-2020-15 | Belvedere Solar | Solar Town LLC | Certification Extension | 2022-11-11 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah10130.pdf
OCS034 | PAC | PP-2020-86 | Round Lake Solar | Round Lake PM LLC | Certification Extension | 2022-10-20 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15575.pdf
SPQ0058 | PGE | PGE-2020-40 | Red Prairie Solar | RP PM LLC | Consent to Collateral Assignment | 2022-10-20 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah16130.pdf
OCS036 | PAC | PP-2020-84 | Pine Grove Solar | Pine Grove PM LLC | Certification Extension | 2022-10-20 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah15575.pdf
CSQ0010 | PGE | PGE-2022-148 | Solar Harvest | Oregon Clean Power Cooperative | Pre-certification Recommendation | 2022-10-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah104356.pdf
CSQ0001 | PGE | PGE-2020-10 | Sheridan Solar | Pacific Northwest Solar LLC | PM Transfer | 2022-09-06 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah95135.pdf
OCS005 | PAC | PP-2020-35 | Wallowa Community Solar | Fleet Development LLC | Waiver to WREGIS registration | 2022-08-23 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah133619.pdf
OCS064 | PAC | PP-2021-122 | McKinley Solar LLC | Sulus Solar | Pre-certification Recommendation | 2022-08-23 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah124853.pdf
OCS037 | PAC | PP-2021-91 | Wayland Solar LLC | Wayland Solar LLC | Certification Extension | 2022-07-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah132928.pdf
SPQ0067 | PGE | PGE-2020-22 | Skyward Solar | Skyward Solar LLC | Certification Extension | 2022-07-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah82552.pdf
OCS027 | PAC | PP-2020-82 | Marble Solar | Marble Solar LLC | Certification Extension | 2022-07-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah132928.pdf
SPQ0193 | PGE | PGE-2020-19 | Dover Solar | Solar Town LLC | PM Transfer | 2022-07-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah82827.pdf
OCS008 | PAC | PP-2020-76 | Burlingame Solar LLC | Burlingame Solar LLC | Certification Extension | 2022-07-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah132928.pdf
SPQ0186 | PGE | PGE-2020-15 | Belvedere Solar | Solar Town LLC | PM Transfer | 2022-07-27 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah82827.pdf
SPQ0193 | PGE | PGE-2020-19 | Dover Solar | Solar Town LLC | Certification Extension | 2022-07-14 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah154054.pdf
SPQ0180 | PGE | PGE-2020-17 | Clayfield Solar LLC | Solar Town LLC | Certification Extension | 2022-07-14 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah154054.pdf
SPQ0186 | PGE | PGE-2020-15 | Belvedere Solar | Solar Town LLC | Certification Extension | 2022-07-14 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah154054.pdf
532 | IP | IP-2020-72 | Verde Light Community Solar | Fleet Development LLC | Certification Extension | 2022-06-29 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah161013.pdf
OCS024 | PAC | PP-2020-81 | Tutuilla Solar | Tutuilla Solar LLC | Certification Extension | 2022-06-29 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah163116.pdf
OCS012 | PAC | PP-2020-63 | Goodling Annex | Bonneville Environmental Foundation | Certification Extension | 2022-06-29 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah102926.pdf
OCS019 | PAC | PP-2020-85 | Wocus Marsh Solar | Wocus Marsh PM LLC | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS020 | PAC | PP-2021-92 | Whisky Creek Solar | Whisky Creek PM LLC | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS047 | PAC | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge Project Manager LLC | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
SPQ0181 | PGE | PGE-2020-45 | Sesqui-C Solar | Sesqui-C Solar | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
SPQ0071 | PGE | PGE-2020-38 | Sandy River Solar | SR PM LLC | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS034 | PAC | PP-2020-86 | Round Lake Solar | Round Lake PM LLC | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS036 | PAC | PP-2020-84 | Pine Grove Solar | Pine Grove PM LLC | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS025 | PAC | PP-2020-80 | Linkville Solar | Linkville PM LLC | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
SPQ0094 | PGE | PGE-2020-42 | Kaiser Creek Solar LLC | Kaiser Creek Project Manager LLC | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
SPQ0164 | PGE | PGE-2020-41 | Fruitland Creek Solar | FC PM LLC | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
SPQ0152 | PGE | PGE-2020-34 | Cosper Creek Solar LLC | Conifer Community Energy 1 LLC | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS044 | PAC | PP-2021-116 | Cherry Creek Solar | Cherry Creek Project Manager LLC | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
SPQ0158 | PGE | PGE-2020-56 | Carnes Creek Solar | Conifer Community Energy 5, LLC | Certification Extension | 2022-06-08 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah9711.pdf
OCS037 | PAC | PP-2021-91 | Wayland Solar LLC | Sulus Solar | PM Transfer | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
SPQ0240 | PGE | PGE-2020-77 | Wallace Solar LLC | Sulus Solar | PM Transfer | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS026 | PAC | PP-2020-87 | Taylor Solar | Sulus Solar | PM Transfer | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS026 | PGE | PP-2020-87 | Taylor Solar | Sulus Solar | PM Transfer | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS057 | PAC | PP-2020-88 | Perrydale Solar | Sulus Solar | PM Transfer | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS027 | PAC | PP-2020-82 | Marble Solar | Sulus Solar | PM Transfer | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS045 | PAC | PP-2021-99 | Green Solar | Sulus Solar | PM Transfer | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS051 | PAC | PP-2022-142 | Canyonville Solar 2 | Sulus Solar | PM Transfer | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS050 | PAC | PP-2021-94 | Canyonville Solar 1 | Sulus Solar | PM Transfer | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS008 | PAC | PP-2020-76 | Burlingame Solar LLC | Sulus Solar | PM Transfer | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
OCS041 | PAC | PP-2021-95 | Burg Solar | Sulus Solar | PM Transfer | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
SPQ0250 | PGE | PGE-2020-75 | Auburn Solar | Sulus Solar | PM Transfer | 2022-06-03 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164641.pdf
CSQ0001 | PGE | PGE-2020-10 | Sheridan Solar | Pacific Northwest Solar LLC | Pre-certification Recommendation | 2022-05-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah164915.pdf
CSQ0001 | PGE | PGE-2020-70 | Jim and Salle's Place Apartments | ROSE Community Development | Certification Recommendation | 2022-05-18 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau22453.pdf
OCS051 | PAC | PP-2022-142 | Canyonville Solar 2 | Sulus Solar | Pre-certification Recommendation | 2022-05-11 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah94645.pdf
OCS050 | PAC | PP-2021-94 | Canyonville Solar 1 | Sulus Solar | Pre-certification Recommendation | 2022-05-11 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah94645.pdf
SPQ0179 | PGE | PGE-2020-18 | Waterford Solar | Solar Town LLC | Pre-certification Recommendation | 2022-04-30 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah162612.pdf
SPQ0220 | PGE | PGE-2020-11 | Cork Solar LLC | Solar Town LLC | Pre-certification Recommendation | 2022-04-30 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah162612.pdf
OCS063 | PAC | PP-2021-103 | Buckaroo Solar 2 | Buckaroo Solar 2 LLC | Pre-certification Recommendation | 2022-04-30 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah162612.pdf
OCS062 | PAC | PP-2021-104 | Buckaroo Solar 1 LLC | Buckaroo Solar 1 LLC | Pre-certification Recommendation | 2022-04-30 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah162612.pdf
SPQ0125 | PGE | PGE-2020-1 | River Valley | Neighborhood Power | Pre-certification Recommendation, with waiver | 2022-04-21 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah165930.pdf
SPQ0163 | PGE | PGE-2020-55 | Zena Solar LLC | Conifer Community Energy 6 LLC | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
SPQ0240 | PGE | PGE-2020-77 | Wallace Solar LLC | Sulus Solar | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS061 | PAC | PP-2020-89 | Reservoir Solar LLC | Sulus Solar | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS057 | PAC | PP-2020-88 | Perrydale Solar | Sulus Solar | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS035 | PAC | PP-2021-111 | Orchard Knob Solar | Orchard Knob Solar LLC | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
CSQ0004 | PGE | PGE-2021-115 | Mompano Solar | Mompano Solar Project Manager LLC | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
SPQ0093 | PGE | PGE-2020-53 | Marquam Creek Solar LLC | Marquam Creek Project Manager LLC | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS039 | PAC | PP-2021-97 | Kelly Creek Solar | Kelly Creek Project Manager LLC | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS018 | PAC | PP-2021-110 | Hay Creek Solar | Hay Creek PM LLC | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
SPQ0157 | PGE | PGE-2020-37 | Gun Club Solar LLC | Conifer Community Energy 2 LLC | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS045 | PAC | PP-2021-99 | Green Solar | Sulus Solar | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS049 | PAC | PP-2021-113 | Chapman Creek Solar | Chapman Creek PM LLC | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS041 | PAC | PP-2021-95 | Burg Solar | Sulus Solar | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
SPQ0191 | PGE | PGE-2020-21 | Buckner Creek Solar LLC | Conifer Community Energy LLC | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
SPQ0250 | PGE | PGE-2020-75 | Auburn Solar | Sulus Solar | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS046 | PAC | PP-2021-109 | Antelope Creek Solar | Antelope Creek PM LLC | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
OCS038 | PAC | PP-2021-112 | 7 Mile Solar | Sulus Solar | Pre-certification Recommendation | 2022-04-15 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah17224.pdf
CSQ0002 | PGE | PGE-2020-70 | Jim and Salle's Place Apartments | ROSE Community Development | Certification Extension | 2022-03-25 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah121349.pdf
SPQ0182 | PGE | PGE-2020-16 | Manchester Solar, LLC | Manchester Solar, LLC | Certification Extension | 2022-02-23 | https://apps.puc.state.or.us/orders/2022ords/22-058.pdf
SPQ0193 | PGE | PGE-2020-19 | Dover Solar | Solar Town LLC | Certification Extension | 2022-02-23 | https://apps.puc.state.or.us/orders/2022ords/22-058.pdf
SPQ0180 | PGE | PGE-2020-17 | Clayfield Solar LLC | Clayfield Solar PM, LLC | Certification Extension | 2022-02-23 | https://apps.puc.state.or.us/orders/2022ords/22-058.pdf
SPQ0186 | PGE | PGE-2020-15 | Belvedere Solar | Belvedere Solar PM, LLC | Certification Extension | 2022-02-23 | https://apps.puc.state.or.us/orders/2022ords/22-058.pdf
OCS005 | PAC | PP-2020-35 | Wallowa Community Solar | Fleet Development LLC | Certification Recommendation | 2022-02-09 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau165511.pdf
OCS074 | PAC | PP-2021-126 | Wood River Solar | Wood River PM, LLC | Pre-certification Recommendation | 2021-12-28 | https://apps.puc.state.or.us/orders/2021ords/21-492.pdf
SPQ0058 | PGE | PGE-2020-40 | Red Prairie Solar | RP PM LLC | Certification Recommendation | 2021-10-06 | https://apps.puc.state.or.us/orders/2021ords/21-321.pdf
OCS042 | PAC | PP-2020-78 | Oregon Shakespeare Festival Community Solar Project | Oregon Clean Power Cooperative | Certification Recommendation | 2021-09-22 | https://apps.puc.state.or.us/orders/2021ords/21-307.pdf
OCS044 | PAC | PP-2021-116 | Cherry Creek Solar | Cherry Creek Project Manager LLC | Pre-certification Recommendation | 2021-07-29 | https://apps.puc.state.or.us/orders/2021ords/21-244.pdf
OCS019 | PAC | PP-2020-85 | Wocus Marsh Solar | Wocus Marsh PM LLC | Pre-certification Recommendation | 2021-04-20 | https://apps.puc.state.or.us/orders/2021ords/21-119.pdf
OCS020 | PAC | PP-2021-92 | Whisky Creek Solar | Whisky Creek PM LLC | Pre-certification Recommendation | 2021-04-20 | https://apps.puc.state.or.us/orders/2021ords/21-119.pdf
OCS047 | PAC | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge Project Manager, LLC | Pre-certification Recommendation | 2021-04-20 | https://apps.puc.state.or.us/orders/2021ords/21-119.pdf
SPQ0166 | PGE | PGE-2020-48 | Williams Acres Solar, LLC | Neighborhood Power | Certification Recommendation | 2021-02-11 | https://apps.puc.state.or.us/orders/2021ords/21-042.pdf
OCS037 | PAC | PP-2021-91 | Wayland Solar LLC | Wayland Solar LLC | Pre-certification Recommendation | 2021-02-11 | https://apps.puc.state.or.us/orders/2021ords/21-046.pdf
SPQ0124 | PGE | PGE-2020-52 | Mt Hope Solar | Neighborhood Power | Certification Recommendation | 2021-02-11 | https://apps.puc.state.or.us/orders/2021ords/21-042.pdf
SPQ0070 | PGE | PGE-2020-51 | Dunn Rd. | Neighborhood Power | Certification Recommendation | 2021-02-11 | https://apps.puc.state.or.us/orders/2021ords/21-042.pdf
OCS026 | PGE | PP-2020-87 | Taylor Solar | Sulus Solar | Pre-certification Recommendation | 2020-12-29 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau10840.pdf
OCS034 | PAC | PP-2020-86 | Round Lake Solar | Round Lake PM LLC | Pre-certification Recommendation | 2020-12-29 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau10840.pdf
OCS036 | PAC | PP-2020-84 | Pine Grove Solar | Pine Grove PM LLC | Pre-certification Recommendation | 2020-12-29 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau10840.pdf
OCS027 | PAC | PP-2020-82 | Marble Solar | Sulus Solar | Pre-certification Recommendation | 2020-12-29 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau10840.pdf
OCS008 | PAC | PP-2020-76 | Burlingame Solar LLC | Sulus Solar | Pre-certification Recommendation | 2020-12-29 | https://edocs.puc.state.or.us/efdocs/HAU/um1930hau10840.pdf
OCS024 | PAC | PP-2020-81 | Tutuilla Solar | Tutuilla Solar LLC | Pre-certification Recommendation | 2020-11-17 | https://apps.puc.state.or.us/orders/2020ords/20-439.pdf
OCS025 | PAC | PP-2020-80 | Linkville Solar | Linkville PM LLC | Pre-certification Recommendation | 2020-11-17 | https://apps.puc.state.or.us/orders/2020ords/20-439.pdf
OCS042 | PAC | PP-2020-78 | Oregon Shakespeare Festival Community Solar Project | Oregon Clean Power Cooperative | Pre-certification Recommendation | 2020-11-05 | https://apps.puc.state.or.us/orders/2020ords/20-414.pdf
532 | IP | IP-2020-72 | Verde Light Community Solar | Fleet Development LLC | Pre-certification Recommendation | 2020-06-18 | https://apps.puc.state.or.us/orders/2020ords/20-201.pdf
SPQ0166 | PGE | PGE-2020-48 | Williams Acres Solar, LLC | Neighborhood Power | Pre-certification Recommendation | 2020-05-07 | https://apps.puc.state.or.us/orders/2020ords/20-159.pdf
SPQ0124 | PGE | PGE-2020-52 | Mt Hope Solar | Neighborhood Power | Pre-certification Recommendation | 2020-05-07 | https://apps.puc.state.or.us/orders/2020ords/20-159.pdf
SPQ0070 | PGE | PGE-2020-51 | Dunn Rd. | Neighborhood Power | Pre-certification Recommendation | 2020-05-07 | https://apps.puc.state.or.us/orders/2020ords/20-159.pdf
OCS005 | PAC | PP-2020-35 | Wallowa Community Solar | Fleet Development LLC | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-141.pdf
SPQ0181 | PGE | PGE-2020-45 | Sesqui-C Solar | Sesqui-C Solar | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-142.pdf
SPQ0071 | PGE | PGE-2020-38 | Sandy River Solar | SR PM LLC | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-142.pdf
Q1045 | PAC | PP-2020-71 | Pilot Rock Solar 2 | Pilot Rock Solar 2 LLC | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-137.pdf
SPQ0094 | PGE | PGE-2020-42 | Kaiser Creek Solar LLC | Kaiser Creek Project Manager LLC | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-142.pdf
CSQ0001 | PGE | PGE-2020-70 | Jim and Salle's Place Apartments | ROSE Community Development | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-137.pdf
CSQ0001 | PGE | PGE-2020-70 | Jim and Salle's Place Apartments | ROSE Community Development | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-137.pdf
OCS012 | PAC | PP-2020-63 | Goodling Annex | Bonneville Environmental Foundation | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-137.pdf
SPQ0164 | PGE | PGE-2020-41 | Fruitland Creek Solar | FC PM LLC | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-142.pdf
SPQ0193 | PGE | PGE-2020-19 | Dover Solar | Solar Town LLC | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-142.pdf
SPQ0152 | PGE | PGE-2020-34 | Cosper Creek Solar LLC | Conifer Community Energy 1 LLC | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-142.pdf
SPQ0180 | PGE | PGE-2020-17 | Clayfield Solar LLC | Solar Town LLC | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-142.pdf
SPQ0158 | PGE | PGE-2020-56 | Carnes Creek Solar | Conifer Community Energy 5 LLC | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-142.pdf
SPQ0186 | PGE | PGE-2020-15 | Belvedere Solar | Solar Town LLC | Pre-certification Recommendation | 2020-04-27 | https://apps.puc.state.or.us/orders/2020ords/20-142.pdf
SPQ0067 | PGE | PGE-2020-22 | Skyward Solar | Skyward Solar LLC | Pre-certification Recommendation | 2020-03-13 | https://apps.puc.state.or.us/orders/2020ords/20-078.pdf
SPQ0058 | PGE | PGE-2020-40 | Red Prairie Solar | RP PM LLC | Pre-certification Recommendation | 2020-03-13 | https://apps.puc.state.or.us/orders/2020ords/20-078.pdf
Q0666 | PAC | PP-2020-13 | Pilot Rock Solar 1 | Pilot Rock Solar 1 LLC | Pre-certification Recommendation | 2020-03-13 | https://apps.puc.state.or.us/orders/2020ords/20-078.pdf

## Questions & Observations (hidden)
Questions
Do PMs have to file for an extension of their operation date?
What is the status of Round lake and Pine Grove?
Can projects fully construct projects before any IX work is completed? Some projects will cite utility delays but have not yet constructed their project (Zena, for example).
Caveats
We only just started really investigating interconnection delays in 2024
Observations
Nearly every project has a change of ownership during the pre-certification phase
Projects have executed construction contracts, building permits in hand, major equipment ordered, interconnection deposits made, 90% subscribed, and may be delayed by many months. Example; Round Lake and Pine Grove was ready to go in September of 2022 and still hasn't been able to come online.
Potential questions to ask at time of cert extensions/ progress reports
Has project construction been completed?
If not, what is outstanding?
Has enrollment been completed?
What is the current enrollment mix?
Has IX construction been completed?
If not, what is outstanding?
Other opportunities for improvement
I've noticed that projects will cite utility delays in their cert extension requests, even when there are other certification requirements that they have yet to meet - like construction, permitting, enrollment. I'd like to provide guidance to project managers that they should be providing an update on all certification requirements that they are still working on meeting when they request pre-cert.
When PM requests an extension, they should provide a status update on all relevant certification requirements

## Support Data (hidden)
Today's Date | 2024-04-01

## Monthly Report Template (hidden)
IX Queue Number | Project ID | Project Name | Project Manager | Utility | Pre-Cert Date | Current Certification Date | Filing Type Type | Reason for Filing | Effective Date | Link to Docket | Previous Waivers, Date, Reason | 6 month update | 12 month update | history of PM transfers | history of previous extension requests | history of waiver requests | has the project file for pre-certification or certification in the previous month | docket link | history of interconnection delays
OCS047 | PP-2021-93 | Sunset Ridge Solar | Sunset Ridge Project Manager, LLC | PAC | 2021-04-20 | 2024-06-11 | Certification Extension | Utility interconnection delays including replacement of a capacitor bank needed, fiber optic design to be completed and fiber optic material to be ordered | 2024-02-22 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326626023.pdf | Extension 1: 6/8/2022, supply chain delays related to US commerce investigation Extension 2: 5/24/2023, interconnection delays- waiting for PPA Extension 3: 11/13/2023, utility interconnection delay (unspecified)
OCS038 | PP-2021-112 | 7 Mile Solar | 7 Mile PM LLC | PAC | 2021-04-20 | 2024-06-11 | Certification Extension | Utility interconnection delays related to fiber optic material that must be ordered and delivered and interconnection designs that are yet to be completed | 2024-02-22 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326626023.pdf
SPQ0163 | PGE-2020-55 | Zena Solar, LLC | Zena Solar, LLC | PGE |  |  | PM Transfer | N/A | 2024-02-21 | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326608023.pdf
SPQ0182 | PGE-2020-16 | Manchester Solar LLC | Manchester Solar LLC | PGE |  |  | Certification Extension | Financing has not been secured |  | https://edocs.puc.state.or.us/efdocs/HAH/um1930hah326851023.pdf

## Jan2024 Snapshot (hidden)
|  | Certified Projects | [6 empty] | Pre Certified Projects
Utility | Carve-out? | # of certified projects | Average time (months) between pre-cert and cert date for certified projects | Min time (months) between pre-cert and cert date for certified projects | Max time between (months) pre-cert and cert date for certified projects | # of projects with time to cert between 18 and 24 months | # of projects with time to cert between 24 and 36 months | # of projects with time to cert >36 months | # of pre-certified projects | Average time (months) between pre-cert and expected cert date for pre-certified projects | Min time (months) between pre-cert and expected cert date for pre-certified projects | Max time (months) between pre-cert and expected cert date for pre-certified projects | # of projects that have
PAC | Yes
PAC | No
PGE | Yes
PGE | No